100 DAYS  •  1,000 APPLICATIONS

# The Full-Time
Second-Job Campaign

A day-by-day execution playbook for Argentina and international markets

| START MON 10 AUG 2026 | FINISH TUE 17 NOV 2026 | TARGET 1,000 VALID APPLICATIONS |
| --- | --- | --- |
| MARKETS 500 AR / 500 INTL | CONTENT 100 BLOG POSTS | BASE PAY ARS 3M / USD 2,500 |

Prepared for

JUAN ROMANO

CAMPAIGN PROMISE Build the complete search system in Days 1–7. From Day 8, submit a precise daily quota, contact decision-makers, publish proof of expertise, and measure every result. Volume never excuses inaccuracy.

VERSION 1.0  •  AUGUST 2026

READ THIS FIRST

# How the campaign works

The rules that keep 1,000 applications useful, ethical, and measurable.

THE TWO PHASES Days 1–7 are a construction sprint with zero applications. Days 8–100 are the execution campaign. Every day—including the build week—publishes one blog post and promotes it on LinkedIn, X, and a manually created Instagram Story.

| Phase | Days | Applications | Primary outcome |
| --- | --- | --- | --- |
| Build | 1–7 | 0 | Assets, profiles, templates, FAQ, tracker, and content system |
| High-volume | 8–77 | 770 | 11/day; alternate 6 AR + 5 Intl and 5 AR + 6 Intl |
| Finish | 78–100 | 230 | 10/day; 5 AR + 5 Intl |
| Total | 1–100 | 1,000 | 500 Argentina + 500 international |

## What counts as an application

Count only a completed submission to one specific, open role. Creating a profile, joining a talent pool, sending a message, or bookmarking a vacancy does not count.

Never count duplicates. A role submitted through a board and again through the company ATS is still one application.

Apply only if the role accepts candidates based in Argentina and you meet roughly 60% or more of the real requirements.

No fabricated skills, dates, titles, employers, scope, or metrics. Every claim must be defensible in an interview.

If a scheduled portal has no valid vacancy, move that slot to a direct company ATS in the same market and record the substitution.

Tailor one priority Argentina application and one priority international application every day. The remaining applications use the closest approved role-family CV.

## Operating assumptions and safeguards

This is a demanding seven-days-a-week plan. Budget about 6–8 focused hours on application days and 7–9 hours during the build sprint. Batch research and content outlines to protect quality.

A second full-time role must be legally and operationally compatible with the current job. Check exclusivity, outside-employment approval, IP assignment, non-compete, schedule overlap, on-call duties, confidentiality, monitoring, and termination clauses before accepting.

Do not mislead either employer. Where policy or contract requires disclosure or permission, obtain it before starting. Never reuse confidential information, code, documents, client names, or equipment.

Never pay to apply, share banking credentials during screening, install unknown software, or continue when a recruiter cannot verify the company and role.

Daily content must be fact-checked and anonymized. Do not publish proprietary architecture, internal incidents, private team information, or unsupported achievements.

If one day is missed, distribute the deficit across the next seven days. The tracker recalculates the required pace; do not submit low-fit applications merely to restore the counter.

## Candidate and AI copilot responsibilities

| Candidate owns | AI copilot supports |
| --- | --- |
| Truth, approvals, final edits, account logins, submissions, messages, publishing, interviews, legal/contract decisions. | JD ranking, ATS keyword comparison, drafts, CV tailoring, cover letters, outreach variants, blog editing, interview practice, tracker analysis. |

AI support happens during active working sessions after the candidate provides the relevant job description, facts, and files; it is not an autonomous promise to act on future days.

## Definition of a completed day

The exact application quota is submitted and logged with working links, source, market, CV version, and next follow-up date.

Four new outreach messages and four follow-ups are sent on application days; one referral request is sent every second application day.

The daily article is published, its link is posted on LinkedIn and X, and the Instagram Story checkbox is completed manually.

Every status change and reply is recorded before the day is closed. The next day begins from the tracker, not from memory.

TARGETS

# Compensation, positioning, and role families

| Market | Base / walk-in target | Good outcome | Excellent outcome | How to state it |
| --- | --- | --- | --- | --- |
| International | USD 2,500/month | USD 3,500–5,000 | USD 6,000–10,000+ | Ask for the approved range first; base is not a ceiling. |
| Argentina | ARS 3,000,000 gross/month | ARS 4,000,000–6,000,000 | ARS 7,000,000+ | Confirm gross/net, benefits, reviews, bonus, and inflation adjustment. |

NEGOTIATION RULE Do not volunteer the minimum. Ask: “What compensation range has been approved for this role?” If pressed, state a target range based on scope, employment type, benefits, currency risk, and schedule—not the lowest acceptable number.

## Six CV role families

| # | Family | Primary evidence |
| --- | --- | --- |
| 01 | Technical Lead / Software Delivery Lead | Delivery, architecture, hands-on guidance, stakeholder alignment |
| 02 | Engineering Manager / Head of Engineering | People leadership, hiring, performance, operating systems, scale |
| 03 | Senior Full-stack Software Engineer | Production engineering across front end, back end, APIs, and data |
| 04 | Platform / DevOps / Observability Engineer | Linux, cloud, containers, monitoring, reliability, incident response |
| 05 | Solutions / Implementation / Technical Account Manager | Discovery, integrations, delivery, customer outcomes, communication |
| 06 | IT Manager / Application Support / Infrastructure Lead | Operations, support, infrastructure, vendors, risk, continuity |

Deliverable: 6 families × English/Spanish × DOCX/PDF/plain text = 36 files. Keep one truth source; versions change emphasis and keywords, never facts.

## Master technology inventory

| Area | Truthful keyword inventory |
| --- | --- |
| Languages & front end | Python; JavaScript; TypeScript; Node.js; React; React Native; Next.js; Angular/AngularJS; Vue; Svelte; jQuery; Ajax; HTML5/CSS3; Bootstrap |
| Back end & frameworks | Django; Flask; Express; NestJS; C#; ASP.NET; ASP.NET Core; .NET Framework; Java; JSP; PHP; Ruby/Rails; Go |
| Additional languages | C; C++; Bash; Batch; Perl; R; Lisp; COBOL; Elixir; Rust; Solidity; Pascal; QuickBasic; Visual Basic; Assembly |
| Data & APIs | SQL/T-SQL/I-SQL; SQL Server; PostgreSQL; MySQL/MariaDB; MongoDB; Cosmos DB; Valkey; GraphQL; ODBC; REST APIs |
| OS & cloud | Linux; Ubuntu; Debian; Red Hat; Fedora; Unix; BSD; Windows/Windows Server; z/OS; Azure; AWS; GCP; OpenStack |
| Containers & observability | Docker/Compose; Kubernetes/k3s; Portainer; Nomad; Zabbix; Grafana; Prometheus; Alertmanager; Loki; Promtail; Uptime Kuma; SNMP; NETCONF; ICMP |
| Infrastructure | Nginx; Apache; PHP-FPM; systemd; OpenSSL; TLS; DNS; dnsmasq; SSH; Samba; Webmin; phpMyAdmin; Veeam; Acronis; Control-M |
| Delivery tooling | Git/GitHub/GitHub Projects; npm/yarn/pnpm; pip/conda; Composer; Bundler; Maven; Gradle; Postman; CI/CD; Jira; Confluence; Scrum; Kanban; Agile |
| Leadership & domains | Architecture; hiring; mentoring; delivery; writing; teaching; open source; banking; ecommerce; logistics; billing; batch operations |
| Monitored/integrated estate | Cisco Meraki/Nexus/SD-WAN/Secure Firewall; Juniper; Palo Alto; Aruba; Ciena; Vyatta; Stormshield; Nutanix; Dell PowerEdge; Pure Storage; EMC Unity; Huawei OceanStor; Nvidia |

KEYWORD DISCIPLINE The master inventory is not copied wholesale into every CV. Each version contains only relevant, supportable technologies, prioritized by the job description and backed by experience or a portfolio artifact.

CHANNEL MAP

# Portal and outreach directory

Every scheduled source is named. A profile or talent-pool registration never counts as an application.

PORTAL AVAILABILITY Websites, eligibility rules, and remote-location filters change. Validate each listing before applying. If a source has no eligible role, use a direct employer ATS in the same market and log the substitution.

## Argentina — job boards and search

| Channel | Home | Use |
| --- | --- | --- |
| LinkedIn Jobs | www.linkedin.com/jobs | Profile + alerts; specific roles only |
| Bumeran | www.bumeran.com.ar | Argentina general board |
| Computrabajo Argentina | ar.computrabajo.com | Argentina general board |
| ZonaJobs | www.zonajobs.com.ar | Argentina general board |
| Indeed Argentina | ar.indeed.com | Search + alerts; verify original source |
| Glassdoor Argentina | www.glassdoor.com.ar/Empleo/index.htm | Jobs + company research |
| Get on Board Argentina | www.getonbrd.com.ar/jobs | Technology roles |
| Torre | torre.ai/jobs | Profile-based matching |
| HiringRoom-powered career pages | www.hiringroom.com | Apply on the employer’s specific career page |

## Argentina — recruiters and communities

| Channel | Home | Use |
| --- | --- | --- |
| Randstad Argentina | www.randstad.com.ar/trabajos | Staffing and direct roles |
| Adecco Argentina | www.adecco.com/es-ar | Staffing and direct roles |
| ManpowerGroup Argentina | www.manpowergroup.com.ar | Staffing and direct roles |
| Experis Argentina | www.experis.com.ar | Technology recruiting |
| Michael Page Argentina | www.michaelpage.com.ar/jobs | Mid/senior and leadership |
| Page Executive | www.pageexecutive.com | Executive search |
| Sysarmy | sysarmy.com | Community; count only a specific vacancy submission |
| Python Argentina / PyAr | www.python.org.ar | Community and networking |
| Nerdearla | nerdearla.com | Community, events, employer discovery |
| r/devsarg | www.reddit.com/r/devsarg | Community leads; verify companies |

## International — remote boards

| Channel | Home | Use |
| --- | --- | --- |
| Get on Board | www.getonbrd.com/jobs | LATAM and global tech |
| Wellfound | wellfound.com/jobs | Startups |
| YC Work at a Startup | www.workatastartup.com/jobs | YC startup roles |
| LATAM Jobs | latamjobs.com | LATAM remote |
| Remote Rocketship | www.remoterocketship.com | Remote discovery |
| We Work Remotely | weworkremotely.com | Remote roles |
| Remote OK | remoteok.com | Remote roles |
| Working Nomads | www.workingnomads.com/jobs | Remote roles |
| Dynamite Jobs | dynamitejobs.com | Remote roles |
| Remotive | remotive.com/remote-jobs | Remote roles |
| Himalayas | himalayas.app/jobs | Remote roles and profiles |
| Jobgether | jobgether.com | Flexible/remote discovery |
| Built In | builtin.com/jobs/remote | Technology roles; check location |
| Welcome to the Jungle | www.welcometothejungle.com/en/jobs | Global discovery; check location |
| JustRemote | justremote.co/remote-jobs | Remote roles |
| Jobspresso | jobspresso.co/remote-work | Curated remote roles |
| Remote.co | remote.co/remote-jobs | Remote roles |
| NoDesk | nodesk.co/remote-jobs | Remote roles |
| DailyRemote | dailyremote.com | Remote roles |
| Crossover | www.crossover.com/jobs | Assessments; verify schedule and terms |

## International — talent networks and firms

| Channel | Home | Use |
| --- | --- | --- |
| LatHire | lathire.com | LATAM talent |
| Puente | www.puentetalent.com | LATAM talent |
| Arc | arc.dev | Remote talent network |
| Turing | www.turing.com | Remote talent network |
| Revelo | www.revelo.com | LATAM talent network |
| Andela | www.andela.com | Global talent network |
| Braintrust | www.usebraintrust.com | Talent marketplace |
| A.Team | www.a.team | Project teams |
| Toptal | www.toptal.com | Screened talent network |
| Lemon.io | lemon.io | Developer network |
| BairesDev | www.bairesdev.com/careers | LATAM/global roles |
| TECLA | www.tecla.io | LATAM remote talent |
| Terminal | www.terminal.io | Remote engineering talent |
| Howdy | www.howdy.com | LATAM talent |
| CloudDevs | clouddevs.com | LATAM talent |
| Proxify | proxify.io | Developer network |
| VanHack | vanhack.com | International tech talent |
| X-Team | x-team.com | Remote developers |
| Nearsure | nearsure.com/careers | LATAM technology roles |
| South | www.hireinsouth.com | LATAM talent |
| Strider | www.onstrider.com | LATAM talent |
| G2i | www.g2i.co | Developer network |
| Gun.io | gun.io | Developer network |
| Lumenalta | lumenalta.com/careers | Digital delivery roles |
| Coderio | www.coderio.com/careers | LATAM technology roles |
| AgileEngine | careers.agileengine.com | Technology roles |
| FullStack Labs | www.fullstack.com/careers | Software consulting roles |
| Dev.Pro | dev.pro/careers | Software consulting roles |
| Encora | careers.encora.com | Digital engineering roles |
| EPAM | www.epam.com/careers | Global engineering roles |
| Globant | career.globant.com | Global technology roles |
| Valtech | www.valtech.com/career | Global digital roles |
| Thoughtworks | www.thoughtworks.com/careers | Global consulting roles |

## Long-term contract marketplaces

| Channel | Home | Use |
| --- | --- | --- |
| Upwork | www.upwork.com | Only long-term/full-time-equivalent opportunities |
| Workana | www.workana.com | LATAM marketplace |
| Contra | contra.com | Independent talent |
| Freelancer | www.freelancer.com | Verify clients carefully |
| Malt | www.malt.com | Independent consulting |
| Guru | www.guru.com | Independent work |
| PeoplePerHour | www.peopleperhour.com | Independent work |

## Direct outreach channels

| Audience | Daily volume | Where to identify them | Purpose |
| --- | --- | --- | --- |
| Argentina recruiter | 1 | LinkedIn, staffing firms, company talent team | Role fit, current openings, referral to owner |
| International recruiter | 1 | LinkedIn, talent networks, company talent team | Argentina eligibility, rate, process |
| Argentina CTO/CEO/hiring manager | 1 | Company leadership page, LinkedIn, community | Concise value hypothesis for one real need |
| International CTO/CEO/hiring manager | 1 | Startup team page, LinkedIn, Wellfound/YC | Relevant evidence and low-friction conversation |
| Referral contact | 1 every 2 days | Former colleagues, clients, university, open source | Warm introduction to a named role |
| Follow-ups | 4 | Tracker due-today view | Polite, specific, one new piece of value |

PRODUCT SPECIFICATION

# The four-tab campaign platform

A simple single-user PHP/MySQL tool for the plan, assets, interview answers, applications, and daily content.

NAVIGATION DECISION The platform has exactly four primary tabs: Plan, Kit, HR FAQ, and Tracker. Daily content lives inside each Plan day, so no additional Content tab is required.

FIXED TECHNOLOGY SCOPE Use PHP, MySQL, Bootstrap, HTML5, CSS3, and vanilla JavaScript only. Pages are rendered by PHP and standard HTML forms write directly to MySQL. There is no API, authentication, JavaScript framework, PHP framework, Node.js build process, cloud service, or external application dependency.

## 1. Plan

Header dashboard: current day, planned/actual applications, cumulative total, remaining to 1,000, Argentina/international split, content streak, replies, interviews, and offers.

Day navigator: Day 1–100 cards with status (Not started, In progress, Done, Blocked, Missed) and a fast jump to Today.

Daily workspace: outcome, candidate tasks, AI-copilot tasks, exact source/count table, outreach checklist, follow-ups, referral requirement, and definition of done.

Content panel: blog title, core angle, outline, article URL, ready X copy, ready LinkedIn copy, Instagram Story manual checkbox, publish timestamps, and channel links.

Evidence: links to submitted applications, tracker records, generated assets, published content, notes, blockers, and carry-forward actions.

## 2. Kit

CV library: 12 content versions and 36 exports; filters for language, family, format, status, last review, and supported keywords.

Templates: cover letters, application notes, recruiter messages, CTO/CEO messages, hiring-manager messages, referral asks, follow-ups, thank-you notes, salary scripts, and availability/contract questions.

Evidence bank: career facts, quantified accomplishments, project summaries, public links, technology inventory, approved stories, references, and red-flag claims requiring verification.

Version control: semantic name, version number, local file path, PDF, plain-text preview, change notes, and “approved for use” switch. Store file metadata in MySQL and the files in a local application folder. Never overwrite the master truth source silently.

## 3. HR FAQ

A bilingual searchable database of 150 classic HR questions with generic reusable answers—not a personal STAR-story database.

Fields: English question, Spanish question, generic English answer, generic Spanish answer, category, what the interviewer evaluates, what to avoid, personalization placeholders, likely follow-ups, difficulty, confidence, favorite, and last practiced.

Modes: browse, bilingual side-by-side, flashcard, random practice, timed mock interview, favorites, low-confidence review, printable view, and CSV export.

Categories: introduction, career history, strengths/weaknesses, motivation, company fit, teamwork, conflict, leadership, failure, remote work, time management, salary, availability, career changes, ethics, and closing questions.

## 4. Tracker

Table and Kanban views. Fields: company, role, market, platform, discovery source, canonical job URL, location eligibility, role family, CV, cover letter, salary/rate, application date, contact, follow-up date, stage, interviews, result, and notes.

Duplicate prevention: normalize company + title + canonical URL; warn before saving a second application to the same role.

Pipeline: Discovered → Selected → Preparing → Applied → Follow-up → Recruiter Screen → Technical → Leadership → Final → Offer → Accepted; alternate endings Rejected or Closed.

Analytics: response, screen, interview, final, and offer rates; conversion by market, portal, role family, CV version, recruiter, and week; median time to reply; overdue follow-ups; reasons for rejection.

Imports/exports: CSV; printable weekly report; MySQL backup. Do not store job-board passwords, banking information, identity documents, or current-employer confidential material.

## Core MySQL tables

| Table | Minimum fields | Key relationship |
| --- | --- | --- |
| DayPlan | day, date, phase, targets, tasks, status, evidence | Has applications, content, contacts, follow-ups |
| Application | company, role, market, source, URL, CV, stage, dates | Belongs to DayPlan; uses CV; may have interviews |
| Portal | name, market, type, URL, profile status, eligibility | Source for applications |
| CV | family, language, format, version, keywords, approved | Used by applications |
| Template | type, language, body, placeholders, version | Used for outreach and cover letters |
| FAQ | questions, answers, category, intent, avoid, confidence | Used in practice sessions |
| ContentPost | day, title, angle, article URL, social copy/status | Belongs to DayPlan |
| Contact | name, company, role, market, channel, consent/notes | Has outreach and follow-ups |
| FollowUp | due, sent, channel, message, outcome | Belongs to application or contact |
| Interview/Offer | type, dates, notes, compensation, decision | Belongs to application |

## Calculations and controls

| Metric / rule | Definition |
| --- | --- |
| Cumulative target | Sum of daily planned applications through the selected day |
| Remaining | 1,000 − valid submitted applications |
| Required pace | Ceiling(remaining ÷ application days remaining) |
| Response rate | Unique human replies ÷ valid applications |
| Interview rate | Applications reaching any interview ÷ valid applications |
| Offer rate | Offers ÷ valid applications |
| Market balance | Argentina submitted vs 500; international submitted vs 500 |
| Content streak | Consecutive days with blog + LinkedIn + X + Instagram Story marked complete |
| Application validation | Specific open role, eligible location, ≥60% fit, no duplicate, truthful CV selected |

## Recommended implementation

| Layer | Recommendation | Reason |
| --- | --- | --- |
| Pages | PHP with server-rendered HTML5 | Simple includes, forms, redirects, and reusable page partials |
| Interface | Bootstrap + CSS3 | Responsive layout, tables, cards, alerts, forms, tabs, and modals |
| Browser logic | Vanilla JavaScript | Filters, counters, confirmation prompts, practice mode, and small UI interactions |
| Database | MySQL | Relational tables, foreign keys, unique indexes, reporting, and campaign totals |
| Data access | PHP PDO prepared statements | Direct server-side MySQL access with validation; no API layer |
| Files | Local application folders | CVs and exports remain local; MySQL stores filename, path, version, and metadata |
| Access | No authentication | Single-user tool restricted to localhost or a trusted private network |
| Backup | mysqldump + CSV exports | Simple local recovery and portable tracker data |

NO-AUTH DEPLOYMENT BOUNDARY Because the platform has no authentication, do not expose it directly to the public internet. Run it on localhost or a trusted private network. If public access ever becomes necessary, authentication must be added before deployment; that is outside this version’s scope.

## MVP acceptance criteria

All 100 days load with their exact quotas, source allocations, tasks, blog titles, X copy, LinkedIn copy, and Instagram checkbox.

Every screen is a PHP page using shared header, navigation, footer, database, validation, and message includes.

The Kit opens or downloads the correct approved local CV and prevents accidental use of an unapproved draft.

HR FAQ searches both languages and runs a JavaScript-assisted practice session while PHP/MySQL performs every save.

Tracker prevents duplicates with MySQL constraints, calculates all totals correctly, and shows 500/500 market progress.

A completed application is saved by a standard PHP POST form and updates both the day counter and dashboard exactly once.

The Bootstrap interface works on mobile, uses explicit Save actions, timestamps changes in Buenos Aires time, and supports mysqldump/CSV backup.

There are no API endpoints, login screens, user tables, tokens, sessions, external services, or framework/build dependencies.

No credential or confidential-employer data is collected. Basic accessibility: keyboard navigation, visible focus, labels, contrast, and non-color status indicators.

DAILY EXECUTION

# Day 1 through Day 100

Build for seven days. Apply for ninety-three. Publish and distribute one useful article every day.

DAILY ORDER Open the Plan tab → process replies and due follow-ups → source and validate roles → tailor priority applications → submit and log → send outreach → complete the special focus → publish the article and social posts → close the day with evidence.

| Day 1 Monday, 10 August 2026 | BUILD 0 applications • construction sprint |
| --- | --- |

Outcome: Complete the English CV system and establish one verified career truth source.

| CANDIDATE — EXECUTE • Collect every current CV, LinkedIn export, project list, public profile, certificate, and portfolio link in one workspace. • Create the Career Facts Sheet: employers, titles, dates, scope, team sizes, technologies, responsibilities, outcomes, and evidence links. Flag anything uncertain. • Approve the six role families and mark technologies as recent production, prior production, learning, or exclude. • Verify every metric and remove confidential names or details that cannot be published. | AI COPILOT — BUILD WITH CANDIDATE • Normalize the Career Facts Sheet and create a master achievement bank using action + context + result + evidence. • Draft six English ATS CVs, each with a role-specific headline, summary, skill order, achievement emphasis, and plain one-column structure. • Build six English keyword banks from 20 representative job descriptions per role family; flag unsupported terms instead of inserting them. • Run initial ATS QA: headings, dates, contact fields, text extraction, no graphics/tables in the CV body, and consistent facts. |
| --- | --- |

DEFINITION OF DONE  Six English CV source files, Career Facts Sheet, achievement bank, technology classification, keyword banks, and completed ATS quality checks.

DAILY BLOG + DISTRIBUTION

| Blog | What Makes a Technical Leader Credible? Core angle: Credibility comes from clear decisions, honest trade-offs, and enough hands-on context to help a team move. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “What Makes a Technical Leader Credible?” Credibility comes from clear decisions, honest trade-offs, and enough hands-on context to help a team move. [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “What Makes a Technical Leader Credible?.” Credibility comes from clear decisions, honest trade-offs, and enough hands-on context to help a team move. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

| Day 2 Tuesday, 11 August 2026 | BUILD 0 applications • construction sprint |
| --- | --- |

Outcome: Complete the Spanish CV system and export the full 36-file ATS package.

| CANDIDATE — EXECUTE • Review terminology for Argentina and international Spanish; preserve titles when translation would distort the real role. • Verify every Spanish statement against the Career Facts Sheet and approve tone, salary language, and availability wording. • Open every DOCX and PDF and confirm page count, contact information, links, dates, accents, and readable filenames. | AI COPILOT — BUILD WITH CANDIDATE • Draft six Spanish ATS CVs matched to the same role families and evidence as the English versions. • Export all 12 versions to DOCX, PDF, and plain text; use stable filenames with family, language, and version. • Compare plain-text extraction against the source, repair broken symbols or reading order, and produce an asset manifest. • Create a one-page selection matrix mapping common job titles to the correct CV family and language. |
| --- | --- |

DEFINITION OF DONE  Twelve approved content versions, 36 usable files, selection matrix, asset manifest, and an organized CV asset library.

DAILY BLOG + DISTRIBUTION

| Blog | What Managing 200 Developers Taught Me About Scale Core angle: At scale, leadership is the design of systems, interfaces, and decision rights—not heroic individual control. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “What Managing 200 Developers Taught Me About Scale” At scale, leadership is the design of systems, interfaces, and decision rights—not heroic individual control. [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “What Managing 200 Developers Taught Me About Scale.” At scale, leadership is the design of systems, interfaces, and decision rights—not heroic individual control. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

| Day 3 Wednesday, 12 August 2026 | BUILD 0 applications • construction sprint |
| --- | --- |

Outcome: Rebuild LinkedIn completely so the profile supports all six role families without becoming vague.

| CANDIDATE — EXECUTE • Approve a primary positioning statement and choose up to five target job titles for Open to Work. • Replace the photo/banner only if needed; confirm location, remote preference, contact method, profile URL, and visibility settings. • Request recommendations from three credible contacts with a specific, easy-to-answer prompt. • Audit all experience, education, licenses, volunteering, publications, projects, languages, and contact information. | AI COPILOT — BUILD WITH CANDIDATE • Rewrite the headline to combine target role, business value, and strongest evidence without keyword stuffing. • Rewrite About in first person: positioning, scale, technical breadth, leadership, current target, and clear contact CTA. • Rewrite each experience entry with a scope line, 3–5 outcome bullets, supported technologies, and no CV contradictions. • Prepare Featured items, 50 prioritized skills, Services if relevant, recruiter-search keywords, and bilingual profile text where useful. |
| --- | --- |

DEFINITION OF DONE  A fully rewritten, internally consistent LinkedIn profile; recommendations requested; recruiter-search settings, Featured items, and skills completed.

DAILY BLOG + DISTRIBUTION

| Blog | From Developer to Manager—and Back to the Code Core angle: Moving between leadership and implementation can strengthen both, when the role and expectations stay explicit. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “From Developer to Manager—and Back to the Code” Moving between leadership and implementation can strengthen both, when the role and expectations stay explicit. [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “From Developer to Manager—and Back to the Code.” Moving between leadership and implementation can strengthen both, when the role and expectations stay explicit. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

| Day 4 Thursday, 13 August 2026 | BUILD 0 applications • construction sprint |
| --- | --- |

Outcome: Rebuild the public proof layer: website, blog presentation, portfolio, and GitHub.

| CANDIDATE — EXECUTE • Choose the public narrative and approve which projects, roles, and technologies can be discussed safely. • Remove or privatize misleading, broken, abandoned, or confidential repositories and links. • Confirm the blog domain, author bio, contact CTA, analytics/privacy choice, and publishing workflow. | AI COPILOT — BUILD WITH CANDIDATE • Rewrite the home page, About, Work/Case Studies, Technology, Writing, and Contact copy around target roles and evidence. • Create three anonymized case-study outlines: leadership/delivery, software/architecture, and platform/observability. • Rewrite GitHub bio and pinned-project READMEs with problem, decisions, run instructions, limitations, and current status. • Create the daily article template: title, thesis, 3 sections, example, practical checklist, CTA, metadata, and social image text. |
| --- | --- |

DEFINITION OF DONE  A coherent website/blog, three case-study outlines, cleaned GitHub, pinned README improvements, and a repeatable publishing workflow.

DAILY BLOG + DISTRIBUTION

| Blog | Why Technical Breadth Still Matters Core angle: Breadth creates better questions and faster pattern recognition; depth turns those patterns into dependable decisions. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “Why Technical Breadth Still Matters” Breadth creates better questions and faster pattern recognition; depth turns those patterns into dependable… [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “Why Technical Breadth Still Matters.” Breadth creates better questions and faster pattern recognition; depth turns those patterns into dependable decisions. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

| Day 5 Friday, 14 August 2026 | BUILD 0 applications • construction sprint |
| --- | --- |

Outcome: Complete the application operating system, outreach/cover-letter kit, tracker, and bilingual classic HR FAQ database.

| CANDIDATE — EXECUTE • Approve message tone, salary boundaries, availability wording, contact channels, and truthful placeholders. • Review 20 representative HR answers and identify where generic wording requires personal facts before use. • Define tracker privacy rules, follow-up cadence, application stages, rejection categories, and evidence requirements. • Test one sample record from discovery through application, follow-up, interview, and offer without counting it as a real application. | AI COPILOT — BUILD WITH CANDIDATE • Create bilingual templates for recruiter, CTO/CEO, hiring manager, referral, first/second follow-up, thank-you, salary, availability, and contract questions. • Create modular English/Spanish cover letters and short application notes with placeholders for company, problem, evidence, and role. • Generate 150 classic HR FAQ rows with English/Spanish questions, generic answers, interviewer intent, what to avoid, personalization placeholders, and follow-ups. • Seed tracker statuses, portal records, CV mapping, metrics, duplicate rules, daily quotas, and CSV import/export samples. |
| --- | --- |

DEFINITION OF DONE  A complete outreach and cover-letter kit; 150-row bilingual generic HR FAQ; tested tracker, follow-up system, KPI formulas, and export samples.

DAILY BLOG + DISTRIBUTION

| Blog | Building a Job-Search Operating System Core angle: A search improves when applications, outreach, content, interviews, and learning share one measurable workflow. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “Building a Job-Search Operating System” A search improves when applications, outreach, content, interviews, and learning share one measurable workflow. [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “Building a Job-Search Operating System.” A search improves when applications, outreach, content, interviews, and learning share one measurable workflow. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

| Day 6 Saturday, 15 August 2026 | BUILD 0 applications • construction sprint |
| --- | --- |

Outcome: Create or fully refresh every Argentina-market profile, alert, recruiter channel, and community entry point.

| CANDIDATE — EXECUTE • Complete profiles on LinkedIn, Bumeran, Computrabajo, ZonaJobs, Indeed Argentina, Glassdoor Argentina, Get on Board Argentina, and Torre. • Register with Randstad, Adecco, ManpowerGroup, Experis, Michael Page, Page Executive, and relevant HiringRoom employer pages; use the correct Spanish CV. • Join or refresh Sysarmy, PyAr, Nerdearla, r/devsarg, relevant React/Node/Linux/DevOps groups, university alumni, and open-source contacts. • Create alerts for all six role families, remote/hybrid Buenos Aires options, and the ARS 3M+ target where the portal supports salary filters. | AI COPILOT — BUILD WITH CANDIDATE • Prepare one reusable profile packet: short/medium/long bio, six headlines, skills, salary, location, availability, links, and role-family CV mapping. • QA every completed profile against the portal checklist; flag missing fields, stale CVs, broken links, and inconsistent dates. • Create the Argentina target-company list, recruiter/contact list, saved-search queries, and portal fallback order. • Draft non-spam community introduction and recruiter connection notes in Spanish. |
| --- | --- |

DEFINITION OF DONE  All supported Argentina profiles or alerts are live, community channels are joined, target-company/recruiter lists exist, and the portal catalog is complete.

DAILY BLOG + DISTRIBUTION

| Blog | How to Turn a Career Into Verifiable Proof Core angle: Hiring decisions become easier when claims point to outcomes, artifacts, scope, and context instead of adjectives. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “How to Turn a Career Into Verifiable Proof” Hiring decisions become easier when claims point to outcomes, artifacts, scope, and context instead of… [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “How to Turn a Career Into Verifiable Proof.” Hiring decisions become easier when claims point to outcomes, artifacts, scope, and context instead of adjectives. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

| Day 7 Sunday, 16 August 2026 | BUILD 0 applications • construction sprint |
| --- | --- |

Outcome: Create or refresh every international channel and finish the complete 100-day editorial and campaign system.

| CANDIDATE — EXECUTE • Complete Tier 1 profiles/alerts: LinkedIn, Get on Board, Wellfound, YC Work at a Startup, LATAM Jobs, Remote Rocketship, We Work Remotely, Remote OK, Working Nomads, Dynamite Jobs, Remotive, Himalayas, and Jobgether. • Complete accounts/alerts where supported on the remaining remote boards; always configure Argentina/LATAM eligibility before saving searches. • Initiate profiles on the listed talent networks and firms; schedule assessments where required. A network acceptance or general profile never counts as an application. • Configure long-term opportunity searches on Upwork, Workana, Contra, Freelancer, Malt, Guru, and PeoplePerHour without chasing short low-value gigs. | AI COPILOT — BUILD WITH CANDIDATE • QA the international profile packet, role titles, USD target, contractor/employee wording, timezone, English CV mapping, links, and eligibility filters. • Finalize all 100 article titles, angles, X posts, LinkedIn promos, and Instagram Story tasks in the campaign content calendar; validate X length and placeholders. • Create the international target-company list, recruiter/executive list, saved-search queries, portal fallback order, and assessment tracker. • Audit the tracker, quotas, templates, portal matrix, content calendar, and outreach lists; export a backup and produce the Day 8 launch checklist. |
| --- | --- |

DEFINITION OF DONE  International channels are ready, screenings are scheduled where needed, the full editorial calendar is complete, and Day 8 can begin from a tested campaign system.

DAILY BLOG + DISTRIBUTION

| Blog | Prepare the System Before You Scale the Search Core angle: A week of disciplined setup can protect quality when application volume rises. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Prepare the System Before You Scale the Search” A week of disciplined setup can protect quality when application volume rises. [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Prepare the System Before You Scale the Search.” A week of disciplined setup can protect quality when application volume rises. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

| Day 8 Monday, 17 August 2026 | LAUNCH 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Launch the application workflow and validate every tracker field with the first 11 submissions.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×2; Bumeran ×1; Computrabajo ×1; ZonaJobs ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | LinkedIn Jobs ×1; Wellfound ×1; Get on Board ×1; Remote OK ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 11 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | What I Learned From My First Application Batch Core angle: The first batch is a calibration experiment: inspect friction, keyword gaps, eligibility, and tracking quality. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “What I Learned From My First Application Batch” The first batch is a calibration experiment: inspect friction, keyword gaps, eligibility, and tracking quality. [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “What I Learned From My First Application Batch.” The first batch is a calibration experiment: inspect friction, keyword gaps, eligibility, and tracking quality. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 11/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 9 Tuesday, 18 August 2026 | LAUNCH 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Audit ATS keyword alignment after real job descriptions; repair only evidence-backed gaps.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Indeed Argentina ×1; Glassdoor Argentina ×1; Get on Board Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | YC Work at a Startup ×2; We Work Remotely ×1; Working Nomads ×1; Dynamite Jobs ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 22 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | ATS Resumes: Clarity Beats Decoration Core angle: Readable structure, relevant language, and truthful evidence matter more than visual tricks. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “ATS Resumes: Clarity Beats Decoration” Readable structure, relevant language, and truthful evidence matter more than visual tricks. [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “ATS Resumes: Clarity Beats Decoration.” Readable structure, relevant language, and truthful evidence matter more than visual tricks. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 22/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 10 Wednesday, 19 August 2026 | LAUNCH 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Test the recruiter message in both markets and record positive, neutral, and negative replies.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Randstad ×2; Adecco ×1; Manpower/Experis ×1; Michael Page ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | Remotive ×1; Himalayas ×1; Jobgether ×1; Built In ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 33 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | How Hiring Managers Scan a Technical CV Core angle: The opening seconds should connect role, scope, stack, outcomes, and recency without forcing interpretation. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “How Hiring Managers Scan a Technical CV” The opening seconds should connect role, scope, stack, outcomes, and recency without forcing interpretation. [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “How Hiring Managers Scan a Technical CV.” The opening seconds should connect role, scope, stack, outcomes, and recency without forcing interpretation. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 33/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 11 Thursday, 20 August 2026 | LAUNCH 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Test CTO/CEO outreach on small companies where the problem and decision-maker are visible.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; HiringRoom employer pages ×1; Bumeran ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Welcome to the Jungle ×2; JustRemote ×1; Jobspresso ×1; Remote.co ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 44 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Python as a Thread Through a Broad Technical Career Core angle: Python is valuable not because it replaces every tool, but because it connects automation, APIs, data, and operations. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “Python as a Thread Through a Broad Technical Career” Python is valuable not because it replaces every tool, but because it connects automation, APIs, data, and… [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “Python as a Thread Through a Broad Technical Career.” Python is valuable not because it replaces every tool, but because it connects automation, APIs, data, and operations. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 44/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 12 Friday, 21 August 2026 | LAUNCH 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Build a fresh target-company list from LinkedIn, communities, and current hiring signals.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Sysarmy vacancy ×2; Nerdearla/company vacancy ×1; r/devsarg verified vacancy ×1; Get on Board Argentina ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | NoDesk ×1; DailyRemote ×1; Remote Rocketship ×1; LATAM Jobs ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 55 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Linux Is Still the Foundation Under Modern Systems Core angle: Cloud abstractions change; process, networking, permissions, filesystems, and observability remain essential. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Linux Is Still the Foundation Under Modern Systems” Cloud abstractions change; process, networking, permissions, filesystems, and observability remain essential. [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Linux Is Still the Foundation Under Modern Systems.” Cloud abstractions change; process, networking, permissions, filesystems, and observability remain essential. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 55/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 13 Saturday, 22 August 2026 | LAUNCH 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Run an Argentina-board deep search and refine location, seniority, and salary filters.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Computrabajo ×1; Indeed Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | LatHire ×2; Puente ×1; Revelo ×1; Andela ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 66 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | What Production Teaches You About Node.js and React Core angle: Production quality lives beyond syntax—in boundaries, failure modes, monitoring, accessibility, and maintainability. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “What Production Teaches You About Node.js and React” Production quality lives beyond syntax—in boundaries, failure modes, monitoring, accessibility, and… [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “What Production Teaches You About Node.js and React.” Production quality lives beyond syntax—in boundaries, failure modes, monitoring, accessibility, and maintainability. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 66/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 14 Sunday, 23 August 2026 | LAUNCH 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Run an international remote-board deep search and eliminate roles that exclude Argentina.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Experis ×2; Michael Page ×1; Glassdoor Argentina ×1; Bumeran ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | Braintrust ×1; A.Team ×1; Arc ×1; Turing ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 77 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Legacy .NET Is Not the Same as Dead Software Core angle: Modernization starts by understanding business value, dependency risk, deployment reality, and safe seams for change. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “Legacy .NET Is Not the Same as Dead Software” Modernization starts by understanding business value, dependency risk, deployment reality, and safe seams for… [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “Legacy .NET Is Not the Same as Dead Software.” Modernization starts by understanding business value, dependency risk, deployment reality, and safe seams for change. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 77/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 15 Monday, 24 August 2026 | LAUNCH 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Complete any pending talent-network screening while applying only to named opportunities.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Bumeran ×1; Computrabajo ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Toptal ×2; Lemon.io ×1; TECLA ×1; Terminal ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 88 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | SQL Outlives Frameworks Core angle: Data models and query behavior often survive multiple application generations, so database judgment compounds. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “SQL Outlives Frameworks” Data models and query behavior often survive multiple application generations, so database judgment compounds. [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “SQL Outlives Frameworks.” Data models and query behavior often survive multiple application generations, so database judgment compounds. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 88/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 16 Tuesday, 25 August 2026 | LAUNCH 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Activate community channels: contribute helpfully, identify specific vacancies, and request one warm introduction.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Indeed Argentina ×2; Glassdoor Argentina ×1; Get on Board Argentina ×1; Torre ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | Howdy ×1; CloudDevs ×1; Proxify ×1; VanHack ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 99 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | How to Work Across Multiple Stacks Without Pretending Core angle: State depth honestly, lead with transferable principles, and show exactly where recent production evidence exists. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “How to Work Across Multiple Stacks Without Pretending” State depth honestly, lead with transferable principles, and show exactly where recent production evidence… [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “How to Work Across Multiple Stacks Without Pretending.” State depth honestly, lead with transferable principles, and show exactly where recent production evidence exists. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 99/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 17 Wednesday, 26 August 2026 | LAUNCH 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Prioritize direct employer career pages and record each company’s ATS and hiring owner.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Randstad ×1; Adecco ×1; Manpower/Experis ×1; Michael Page ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | X-Team ×2; Nearsure ×1; South ×1; Strider ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 110 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Engineering Management Changes With Team Scale Core angle: The practices that work for six people can fail at sixty; leadership mechanisms must evolve with coordination cost. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Engineering Management Changes With Team Scale” The practices that work for six people can fail at sixty; leadership mechanisms must evolve with coordination… [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Engineering Management Changes With Team Scale.” The practices that work for six people can fail at sixty; leadership mechanisms must evolve with coordination cost. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 110/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 18 Thursday, 27 August 2026 | LAUNCH 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Contact staffing firms with a concise bilingual profile and verify the exact roles they represent.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×2; HiringRoom employer pages ×1; Bumeran ×1; ZonaJobs ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | G2i ×1; Gun.io ×1; Lumenalta ×1; Coderio ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 121 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Cold Outreach Without Becoming Spam Core angle: Relevant context, a specific hypothesis, credible evidence, and an easy next step make outreach respectful. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “Cold Outreach Without Becoming Spam” Relevant context, a specific hypothesis, credible evidence, and an easy next step make outreach respectful. [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “Cold Outreach Without Becoming Spam.” Relevant context, a specific hypothesis, credible evidence, and an easy next step make outreach respectful. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 121/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 19 Friday, 28 August 2026 | LAUNCH 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Tune all saved searches and alerts; remove noisy queries and add missing role-family keywords.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Sysarmy vacancy ×1; Nerdearla/company vacancy ×1; r/devsarg verified vacancy ×1; Get on Board Argentina ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | AgileEngine ×2; FullStack Labs ×1; Dev.Pro ×1; Encora ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 132 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | When It Makes Sense to Contact a Founder Directly Core angle: Founder outreach works when the company is small, the problem is visible, and the message offers substance rather than entitlement. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “When It Makes Sense to Contact a Founder Directly” Founder outreach works when the company is small, the problem is visible, and the message offers substance… [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “When It Makes Sense to Contact a Founder Directly.” Founder outreach works when the company is small, the problem is visible, and the message offers substance rather than entitlement. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 132/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 20 Saturday, 29 August 2026 | LAUNCH 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Review the first reply data and change one variable only: source, CV, role family, or message.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×2; Computrabajo ×1; Indeed Argentina ×1; Torre ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | EPAM ×1; Globant ×1; Valtech ×1; Thoughtworks ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 143 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Recruiters Are Partners, Not Application Routers Core angle: Clear positioning, responsiveness, and honest constraints help recruiters represent a candidate accurately. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “Recruiters Are Partners, Not Application Routers” Clear positioning, responsiveness, and honest constraints help recruiters represent a candidate accurately. [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “Recruiters Are Partners, Not Application Routers.” Clear positioning, responsiveness, and honest constraints help recruiters represent a candidate accurately. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 143/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 21 Sunday, 30 August 2026 | LAUNCH 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Complete the first weekly audit: totals, duplicates, eligibility, response rate, and energy cost.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Experis ×1; Michael Page ×1; Glassdoor Argentina ×1; Bumeran ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Upwork long-term ×2; Workana long-term ×1; Contra long-term ×1; Malt long-term ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 154 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Measure the Job Search Like a Product Funnel Core angle: Track conversion by source and role family so activity turns into learning, not just a larger counter. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “Measure the Job Search Like a Product Funnel” Track conversion by source and role family so activity turns into learning, not just a larger counter. [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “Measure the Job Search Like a Product Funnel.” Track conversion by source and role family so activity turns into learning, not just a larger counter. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 154/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 22 Monday, 31 August 2026 | OPTIMIZE 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Compare Argentina channel conversion and redirect one weak source slot to the strongest valid source.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×2; Bumeran ×1; Computrabajo ×1; ZonaJobs ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | LinkedIn Jobs ×1; Wellfound ×1; Get on Board ×1; Remote OK ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 165 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Modernizing Legacy Systems Without Breaking the Business Core angle: Successful modernization protects continuity while reducing risk in small, observable increments. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Modernizing Legacy Systems Without Breaking the Business” Successful modernization protects continuity while reducing risk in small, observable increments. [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Modernizing Legacy Systems Without Breaking the Business.” Successful modernization protects continuity while reducing risk in small, observable increments. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 165/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 23 Tuesday, 01 September 2026 | OPTIMIZE 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Compare international channel conversion and redirect one weak source slot without changing the market split.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Indeed Argentina ×1; Glassdoor Argentina ×1; Get on Board Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | YC Work at a Startup ×2; We Work Remotely ×1; Working Nomads ×1; Dynamite Jobs ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 176 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Technical Debt Is a Portfolio, Not a Moral Failure Core angle: Debt decisions should compare interest, probability, business impact, and opportunity cost. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “Technical Debt Is a Portfolio, Not a Moral Failure” Debt decisions should compare interest, probability, business impact, and opportunity cost. [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “Technical Debt Is a Portfolio, Not a Moral Failure.” Debt decisions should compare interest, probability, business impact, and opportunity cost. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 176/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 24 Wednesday, 02 September 2026 | OPTIMIZE 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Review senior full-stack demand and strengthen public evidence for the most requested truthful stack.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Randstad ×2; Adecco ×1; Manpower/Experis ×1; Michael Page ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | Remotive ×1; Himalayas ×1; Jobgether ×1; Built In ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 187 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Observability Is a Management System Core angle: Shared signals improve prioritization, accountability, incident learning, and communication beyond operations teams. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “Observability Is a Management System” Shared signals improve prioritization, accountability, incident learning, and communication beyond operations… [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “Observability Is a Management System.” Shared signals improve prioritization, accountability, incident learning, and communication beyond operations teams. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 187/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 25 Thursday, 03 September 2026 | OPTIMIZE 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Review Tech Lead and delivery roles; clarify scope, architecture, and stakeholder outcomes in the priority CV.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; HiringRoom employer pages ×1; Bumeran ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Welcome to the Jungle ×2; JustRemote ×1; Jobspresso ×1; Remote.co ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 198 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | What Zabbix Teaches About Operational Reality Core angle: Monitoring becomes useful when discovery, ownership, thresholds, dependencies, and response paths match the real estate. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “What Zabbix Teaches About Operational Reality” Monitoring becomes useful when discovery, ownership, thresholds, dependencies, and response paths match the… [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “What Zabbix Teaches About Operational Reality.” Monitoring becomes useful when discovery, ownership, thresholds, dependencies, and response paths match the real estate. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 198/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 26 Friday, 04 September 2026 | OPTIMIZE 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Review Engineering Manager roles; make team scale, hiring, performance, and delivery mechanisms explicit.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Sysarmy vacancy ×2; Nerdearla/company vacancy ×1; r/devsarg verified vacancy ×1; Get on Board Argentina ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | NoDesk ×1; DailyRemote ×1; Remote Rocketship ×1; LATAM Jobs ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 209 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Prometheus and Grafana: From Metrics to Decisions Core angle: Dashboards matter only when metrics connect symptoms, service objectives, and an action somebody owns. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “Prometheus and Grafana: From Metrics to Decisions” Dashboards matter only when metrics connect symptoms, service objectives, and an action somebody owns. [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “Prometheus and Grafana: From Metrics to Decisions.” Dashboards matter only when metrics connect symptoms, service objectives, and an action somebody owns. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 209/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 27 Saturday, 05 September 2026 | OPTIMIZE 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Review Platform/DevOps roles; connect Linux, cloud, containers, monitoring, and incidents to outcomes.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Computrabajo ×1; Indeed Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | LatHire ×2; Puente ×1; Revelo ×1; Andela ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 220 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Logs With Loki: Design for Questions, Not Volume Core angle: Good logging starts with the questions teams need to answer and the labels they can afford. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Logs With Loki: Design for Questions, Not Volume” Good logging starts with the questions teams need to answer and the labels they can afford. [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Logs With Loki: Design for Questions, Not Volume.” Good logging starts with the questions teams need to answer and the labels they can afford. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 220/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 28 Sunday, 06 September 2026 | OPTIMIZE 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Review Solutions/TAM roles; connect discovery, integrations, communication, and customer outcomes.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Experis ×2; Michael Page ×1; Glassdoor Argentina ×1; Bumeran ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | Braintrust ×1; A.Team ×1; Arc ×1; Turing ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 231 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Why I Keep a Linux Homelab Core angle: A homelab makes infrastructure knowledge concrete through safe experiments with networking, services, failure, and recovery. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “Why I Keep a Linux Homelab” A homelab makes infrastructure knowledge concrete through safe experiments with networking, services, failure,… [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “Why I Keep a Linux Homelab.” A homelab makes infrastructure knowledge concrete through safe experiments with networking, services, failure, and recovery. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 231/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 29 Monday, 07 September 2026 | OPTIMIZE 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Review IT/application-support roles; show operational ownership, continuity, vendors, and risk.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Bumeran ×1; Computrabajo ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Toptal ×2; Lemon.io ×1; TECLA ×1; Terminal ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 242 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Docker Is a Delivery Contract Core angle: Containers are most useful when they make runtime assumptions explicit and repeatable across environments. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “Docker Is a Delivery Contract” Containers are most useful when they make runtime assumptions explicit and repeatable across environments. [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “Docker Is a Delivery Contract.” Containers are most useful when they make runtime assumptions explicit and repeatable across environments. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 242/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 30 Tuesday, 08 September 2026 | OPTIMIZE 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Run a direct-ATS sprint against 25 researched target companies and submit only eligible openings.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Indeed Argentina ×2; Glassdoor Argentina ×1; Get on Board Argentina ×1; Torre ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | Howdy ×1; CloudDevs ×1; Proxify ×1; VanHack ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 253 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Kubernetes and k3s: Complexity Must Earn Its Place Core angle: Orchestration should solve a real operational problem; smaller systems often deserve smaller control planes. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “Kubernetes and k3s: Complexity Must Earn Its Place” Orchestration should solve a real operational problem; smaller systems often deserve smaller control planes. [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “Kubernetes and k3s: Complexity Must Earn Its Place.” Orchestration should solve a real operational problem; smaller systems often deserve smaller control planes. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 253/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 31 Wednesday, 09 September 2026 | OPTIMIZE 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Ask five warm contacts for role intelligence; send the single scheduled referral request to the best fit.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Randstad ×1; Adecco ×1; Manpower/Experis ×1; Michael Page ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | X-Team ×2; Nearsure ×1; South ×1; Strider ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 264 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | DNS and TLS: The Quiet Dependencies Behind Everything Core angle: Many ‘application’ incidents are really failures of naming, certificates, time, routing, or trust. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “DNS and TLS: The Quiet Dependencies Behind Everything” Many ‘application’ incidents are really failures of naming, certificates, time, routing, or trust. [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “DNS and TLS: The Quiet Dependencies Behind Everything.” Many ‘application’ incidents are really failures of naming, certificates, time, routing, or trust. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 264/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 32 Thursday, 10 September 2026 | OPTIMIZE 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Improve the cover-letter decision rule: write one only when requested or when it adds material context.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×2; HiringRoom employer pages ×1; Bumeran ×1; ZonaJobs ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | G2i ×1; Gun.io ×1; Lumenalta ×1; Coderio ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 275 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Backups Are Promises Until Restore Day Core angle: A backup strategy is credible only when restores, ownership, retention, and recovery objectives are tested. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Backups Are Promises Until Restore Day” A backup strategy is credible only when restores, ownership, retention, and recovery objectives are tested. [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Backups Are Promises Until Restore Day.” A backup strategy is credible only when restores, ownership, retention, and recovery objectives are tested. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 275/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 33 Friday, 11 September 2026 | OPTIMIZE 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Audit application speed and accuracy; remove repeated manual work with approved snippets and fields.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Sysarmy vacancy ×1; Nerdearla/company vacancy ×1; r/devsarg verified vacancy ×1; Get on Board Argentina ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | AgileEngine ×2; FullStack Labs ×1; Dev.Pro ×1; Encora ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 286 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Incident Response Starts Before the Incident Core angle: Roles, signals, runbooks, communication paths, and decision authority should exist before pressure arrives. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “Incident Response Starts Before the Incident” Roles, signals, runbooks, communication paths, and decision authority should exist before pressure arrives. [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “Incident Response Starts Before the Incident.” Roles, signals, runbooks, communication paths, and decision authority should exist before pressure arrives. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 286/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 34 Saturday, 12 September 2026 | OPTIMIZE 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Review rejection reasons without guessing; tag stage, known reason, hypothesis, and next experiment separately.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×2; Computrabajo ×1; Indeed Argentina ×1; Torre ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | EPAM ×1; Globant ×1; Valtech ×1; Thoughtworks ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 297 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Monitor Business Services, Not Just Devices Core angle: Infrastructure signals become valuable when mapped to customer journeys, transactions, and service impact. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “Monitor Business Services, Not Just Devices” Infrastructure signals become valuable when mapped to customer journeys, transactions, and service impact. [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “Monitor Business Services, Not Just Devices.” Infrastructure signals become valuable when mapped to customer journeys, transactions, and service impact. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 297/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 35 Sunday, 13 September 2026 | OPTIMIZE 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Run the second weekly audit and freeze any channel that produces invalid or duplicate listings.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Experis ×1; Michael Page ×1; Glassdoor Argentina ×1; Bumeran ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Upwork long-term ×2; Workana long-term ×1; Contra long-term ×1; Malt long-term ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 308 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | What a Technical Lead Actually Does Core angle: A tech lead reduces uncertainty through technical direction, coordination, feedback, and timely decisions. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “What a Technical Lead Actually Does” A tech lead reduces uncertainty through technical direction, coordination, feedback, and timely decisions. [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “What a Technical Lead Actually Does.” A tech lead reduces uncertainty through technical direction, coordination, feedback, and timely decisions. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 308/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 36 Monday, 14 September 2026 | INTERVIEW 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Build the 30-second, 90-second, and 3-minute professional introduction in English and Spanish.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×2; Bumeran ×1; Computrabajo ×1; ZonaJobs ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | LinkedIn Jobs ×1; Wellfound ×1; Get on Board ×1; Remote OK ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 319 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | The Hands-On Engineering Manager: Useful or Dangerous? Core angle: Hands-on work helps when it removes ambiguity; it hurts when it steals ownership or becomes a hidden second role. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “The Hands-On Engineering Manager: Useful or Dangerous?” Hands-on work helps when it removes ambiguity; it hurts when it steals ownership or becomes a hidden second… [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “The Hands-On Engineering Manager: Useful or Dangerous?.” Hands-on work helps when it removes ambiguity; it hurts when it steals ownership or becomes a hidden second role. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 319/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 37 Tuesday, 15 September 2026 | INTERVIEW 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Create five generic HR-answer personalizations while keeping the reusable FAQ answers intact.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Indeed Argentina ×1; Glassdoor Argentina ×1; Get on Board Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | YC Work at a Startup ×2; We Work Remotely ×1; Working Nomads ×1; Dynamite Jobs ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 330 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Delegation Is an Interface Design Problem Core angle: Clear outcomes, boundaries, context, feedback loops, and escalation paths make delegation reliable. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Delegation Is an Interface Design Problem” Clear outcomes, boundaries, context, feedback loops, and escalation paths make delegation reliable. [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Delegation Is an Interface Design Problem.” Clear outcomes, boundaries, context, feedback loops, and escalation paths make delegation reliable. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 330/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 38 Wednesday, 16 September 2026 | INTERVIEW 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Prepare leadership stories: hiring, delegation, conflict, performance, failure, and organizational change.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Randstad ×2; Adecco ×1; Manpower/Experis ×1; Michael Page ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | Remotive ×1; Himalayas ×1; Jobgether ×1; Built In ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 341 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Documentation Is Part of the System Core angle: Documentation should reduce repeated decisions and operational risk, not become an archive nobody trusts. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “Documentation Is Part of the System” Documentation should reduce repeated decisions and operational risk, not become an archive nobody trusts. [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “Documentation Is Part of the System.” Documentation should reduce repeated decisions and operational risk, not become an archive nobody trusts. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 341/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 39 Thursday, 17 September 2026 | INTERVIEW 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Prepare delivery stories: prioritization, estimation, dependency, rescue, stakeholder disagreement, and outcome.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; HiringRoom employer pages ×1; Bumeran ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Welcome to the Jungle ×2; JustRemote ×1; Jobspresso ×1; Remote.co ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 352 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | How to Make Architecture Decisions Reversible Core angle: Identify which choices are hard to undo, time-box evidence gathering, and record assumptions for later review. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “How to Make Architecture Decisions Reversible” Identify which choices are hard to undo, time-box evidence gathering, and record assumptions for later review. [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “How to Make Architecture Decisions Reversible.” Identify which choices are hard to undo, time-box evidence gathering, and record assumptions for later review. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 352/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 40 Friday, 18 September 2026 | INTERVIEW 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Prepare architecture stories: constraints, alternatives, decision, migration, reliability, and trade-offs.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Sysarmy vacancy ×2; Nerdearla/company vacancy ×1; r/devsarg verified vacancy ×1; Get on Board Argentina ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | NoDesk ×1; DailyRemote ×1; Remote Rocketship ×1; LATAM Jobs ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 363 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Translate Technical Risk for Business Stakeholders Core angle: Good communication connects probability and impact to choices, cost, timing, and customer outcomes. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “Translate Technical Risk for Business Stakeholders” Good communication connects probability and impact to choices, cost, timing, and customer outcomes. [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “Translate Technical Risk for Business Stakeholders.” Good communication connects probability and impact to choices, cost, timing, and customer outcomes. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 363/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 41 Saturday, 19 September 2026 | INTERVIEW 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Prepare incident stories: detection, coordination, mitigation, communication, root cause, and prevention.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Computrabajo ×1; Indeed Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | LatHire ×2; Puente ×1; Revelo ×1; Andela ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 374 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | One-on-Ones Are a Leadership Sensor Core angle: Consistent one-on-ones reveal friction, growth needs, context gaps, and emerging risks before dashboards do. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “One-on-Ones Are a Leadership Sensor” Consistent one-on-ones reveal friction, growth needs, context gaps, and emerging risks before dashboards do. [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “One-on-Ones Are a Leadership Sensor.” Consistent one-on-ones reveal friction, growth needs, context gaps, and emerging risks before dashboards do. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 374/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 42 Sunday, 20 September 2026 | INTERVIEW 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Prepare hands-on stories across Python, JavaScript/TypeScript, .NET, SQL, Linux, and APIs.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Experis ×2; Michael Page ×1; Glassdoor Argentina ×1; Bumeran ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | Braintrust ×1; A.Team ×1; Arc ×1; Turing ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 385 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Hiring for Evidence, Learning, and Judgment Core angle: Strong interviews distinguish memorized vocabulary from real decisions, feedback, and the capacity to learn. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Hiring for Evidence, Learning, and Judgment” Strong interviews distinguish memorized vocabulary from real decisions, feedback, and the capacity to learn. [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Hiring for Evidence, Learning, and Judgment.” Strong interviews distinguish memorized vocabulary from real decisions, feedback, and the capacity to learn. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 385/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 43 Monday, 21 September 2026 | INTERVIEW 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Run a bilingual HR mock interview; score clarity, relevance, length, defensibility, and confidence.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Bumeran ×1; Computrabajo ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Toptal ×2; Lemon.io ×1; TECLA ×1; Terminal ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 396 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Performance Management Should Not Contain Surprises Core angle: Expectations, examples, feedback, support, and consequences should be timely and documented. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “Performance Management Should Not Contain Surprises” Expectations, examples, feedback, support, and consequences should be timely and documented. [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “Performance Management Should Not Contain Surprises.” Expectations, examples, feedback, support, and consequences should be timely and documented. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 396/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 44 Tuesday, 22 September 2026 | INTERVIEW 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Run a system-design mock: requirements, scale, data, interfaces, failure, security, observability, and cost.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Indeed Argentina ×2; Glassdoor Argentina ×1; Get on Board Argentina ×1; Torre ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | Howdy ×1; CloudDevs ×1; Proxify ×1; VanHack ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 407 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | A Useful Way to Talk About Failure Core angle: Explain the decision context, your responsibility, the consequence, the correction, and what changed afterward. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “A Useful Way to Talk About Failure” Explain the decision context, your responsibility, the consequence, the correction, and what changed afterward. [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “A Useful Way to Talk About Failure.” Explain the decision context, your responsibility, the consequence, the correction, and what changed afterward. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 407/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 45 Wednesday, 23 September 2026 | INTERVIEW 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Run a technical-leadership mock with ambiguous priorities and conflicting stakeholder constraints.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Randstad ×1; Adecco ×1; Manpower/Experis ×1; Michael Page ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | X-Team ×2; Nearsure ×1; South ×1; Strider ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 418 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Why Software Estimates Need Ranges Core angle: Ranges make uncertainty visible and support decisions better than false precision. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “Why Software Estimates Need Ranges” Ranges make uncertainty visible and support decisions better than false precision. [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “Why Software Estimates Need Ranges.” Ranges make uncertainty visible and support decisions better than false precision. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 418/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 46 Thursday, 24 September 2026 | INTERVIEW 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Create a company-research one-pager for every active interview and attach it to the tracker.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×2; HiringRoom employer pages ×1; Bumeran ×1; ZonaJobs ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | G2i ×1; Gun.io ×1; Lumenalta ×1; Coderio ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 429 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Delivery Is a System, Not a Sprint Ceremony Core angle: Flow depends on prioritization, decision latency, quality, dependencies, and feedback—not meeting labels. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “Delivery Is a System, Not a Sprint Ceremony” Flow depends on prioritization, decision latency, quality, dependencies, and feedback—not meeting labels. [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “Delivery Is a System, Not a Sprint Ceremony.” Flow depends on prioritization, decision latency, quality, dependencies, and feedback—not meeting labels. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 429/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 47 Friday, 25 September 2026 | INTERVIEW 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Send concise post-interview thank-you notes that restate one relevant value point without pressure.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Sysarmy vacancy ×1; Nerdearla/company vacancy ×1; r/devsarg verified vacancy ×1; Get on Board Argentina ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | AgileEngine ×2; FullStack Labs ×1; Dev.Pro ×1; Encora ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 440 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Design Teams Around Ownership Boundaries Core angle: Team structure works best when authority, skills, dependencies, and service boundaries reinforce each other. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Design Teams Around Ownership Boundaries” Team structure works best when authority, skills, dependencies, and service boundaries reinforce each other. [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Design Teams Around Ownership Boundaries.” Team structure works best when authority, skills, dependencies, and service boundaries reinforce each other. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 440/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 48 Saturday, 26 September 2026 | INTERVIEW 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Review interview conversion by role family and correct positioning before adding new materials.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×2; Computrabajo ×1; Indeed Argentina ×1; Torre ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | EPAM ×1; Globant ×1; Valtech ×1; Thoughtworks ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 451 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | The Hardest Lesson From Leading 200 Developers Core angle: Scale magnifies unclear ownership and inconsistent mechanisms faster than it magnifies individual talent. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “The Hardest Lesson From Leading 200 Developers” Scale magnifies unclear ownership and inconsistent mechanisms faster than it magnifies individual talent. [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “The Hardest Lesson From Leading 200 Developers.” Scale magnifies unclear ownership and inconsistent mechanisms faster than it magnifies individual talent. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 451/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 49 Sunday, 27 September 2026 | INTERVIEW 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Run the third weekly audit; preserve winning patterns and write one test for the next week.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Experis ×1; Michael Page ×1; Glassdoor Argentina ×1; Bumeran ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Upwork long-term ×2; Workana long-term ×1; Contra long-term ×1; Malt long-term ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 462 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Remote Teams Need More Explicit Interfaces Core angle: Remote work rewards written context, visible decisions, clear availability, and intentional social connection. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “Remote Teams Need More Explicit Interfaces” Remote work rewards written context, visible decisions, clear availability, and intentional social connection. [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “Remote Teams Need More Explicit Interfaces.” Remote work rewards written context, visible decisions, clear availability, and intentional social connection. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 462/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 50 Monday, 28 September 2026 | DEPTH 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Create a public architecture case study with anonymized requirements, trade-offs, and measurable outcomes.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×2; Bumeran ×1; Computrabajo ×1; ZonaJobs ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | LinkedIn Jobs ×1; Wellfound ×1; Get on Board ×1; Remote OK ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 473 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | How to Enter an Unfamiliar Production System Core angle: Start with users, architecture, deploy path, dependencies, telemetry, recent incidents, and safe ways to observe. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “How to Enter an Unfamiliar Production System” Start with users, architecture, deploy path, dependencies, telemetry, recent incidents, and safe ways to… [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “How to Enter an Unfamiliar Production System.” Start with users, architecture, deploy path, dependencies, telemetry, recent incidents, and safe ways to observe. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 473/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 51 Tuesday, 29 September 2026 | DEPTH 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Create a Linux/operations artifact: runbook, diagnostic guide, or safe homelab walkthrough.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Indeed Argentina ×1; Glassdoor Argentina ×1; Get on Board Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | YC Work at a Startup ×2; We Work Remotely ×1; Working Nomads ×1; Dynamite Jobs ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 484 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Python and Django for Durable Business Systems Core angle: The strength of a mature stack is the speed of making conventional, understandable choices. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “Python and Django for Durable Business Systems” The strength of a mature stack is the speed of making conventional, understandable choices. [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “Python and Django for Durable Business Systems.” The strength of a mature stack is the speed of making conventional, understandable choices. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 484/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 52 Wednesday, 30 September 2026 | DEPTH 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Create an observability artifact linking service objectives, metrics, logs, dashboards, and response.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Randstad ×2; Adecco ×1; Manpower/Experis ×1; Michael Page ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | Remotive ×1; Himalayas ×1; Jobgether ×1; Built In ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 495 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Flask APIs: Small Framework, Serious Responsibilities Core angle: A lightweight framework still needs authentication, validation, observability, testing, and operational ownership. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Flask APIs: Small Framework, Serious Responsibilities” A lightweight framework still needs authentication, validation, observability, testing, and operational… [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Flask APIs: Small Framework, Serious Responsibilities.” A lightweight framework still needs authentication, validation, observability, testing, and operational ownership. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 495/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 53 Thursday, 01 October 2026 | DEPTH 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Create a concise API/data artifact showing contracts, validation, failure handling, and operational concerns.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; HiringRoom employer pages ×1; Bumeran ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Welcome to the Jungle ×2; JustRemote ×1; Jobspresso ×1; Remote.co ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 506 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | JavaScript and TypeScript: Make Boundaries Explicit Core angle: Types help most at module, API, event, and persistence boundaries where misunderstandings become production failures. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “JavaScript and TypeScript: Make Boundaries Explicit” Types help most at module, API, event, and persistence boundaries where misunderstandings become production… [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “JavaScript and TypeScript: Make Boundaries Explicit.” Types help most at module, API, event, and persistence boundaries where misunderstandings become production failures. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 506/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 54 Friday, 02 October 2026 | DEPTH 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Review GitHub pinned work, README clarity, licenses, dates, and the relationship to target roles.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Sysarmy vacancy ×2; Nerdearla/company vacancy ×1; r/devsarg verified vacancy ×1; Get on Board Argentina ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | NoDesk ×1; DailyRemote ×1; Remote Rocketship ×1; LATAM Jobs ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 517 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | React Beyond Components Core angle: Sustainable React systems need state discipline, accessibility, performance budgets, testing, and clear ownership. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “React Beyond Components” Sustainable React systems need state discipline, accessibility, performance budgets, testing, and clear… [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “React Beyond Components.” Sustainable React systems need state discipline, accessibility, performance budgets, testing, and clear ownership. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 517/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 55 Saturday, 03 October 2026 | DEPTH 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Ask active recruiters which missing evidence blocks progression; distinguish feedback from personal preference.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Computrabajo ×1; Indeed Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | LatHire ×2; Puente ×1; Revelo ×1; Andela ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 528 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Node.js: Concurrency Is a Design Constraint Core angle: Event-driven performance is powerful when blocking work, backpressure, failures, and resource limits are understood. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “Node.js: Concurrency Is a Design Constraint” Event-driven performance is powerful when blocking work, backpressure, failures, and resource limits are… [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “Node.js: Concurrency Is a Design Constraint.” Event-driven performance is powerful when blocking work, backpressure, failures, and resource limits are understood. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 528/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 56 Sunday, 04 October 2026 | DEPTH 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Practice salary range, contractor/employee, currency, benefits, inflation, and review-cycle questions.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Experis ×2; Michael Page ×1; Glassdoor Argentina ×1; Bumeran ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | Braintrust ×1; A.Team ×1; Arc ×1; Turing ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 539 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | C# and .NET Across Generations Core angle: The useful modernization question is how to preserve behavior while improving runtime, deployment, tests, and maintainability. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “C# and .NET Across Generations” The useful modernization question is how to preserve behavior while improving runtime, deployment, tests, and… [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “C# and .NET Across Generations.” The useful modernization question is how to preserve behavior while improving runtime, deployment, tests, and maintainability. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 539/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 57 Monday, 05 October 2026 | DEPTH 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Practice the outside-employment and availability conversation truthfully; list contract questions for counsel if needed.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Bumeran ×1; Computrabajo ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Toptal ×2; Lemon.io ×1; TECLA ×1; Terminal ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 550 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | SQL Server and PostgreSQL: Choose With Context Core angle: Operational knowledge, team skills, workloads, ecosystem, and migration cost matter more than database tribalism. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “SQL Server and PostgreSQL: Choose With Context” Operational knowledge, team skills, workloads, ecosystem, and migration cost matter more than database… [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “SQL Server and PostgreSQL: Choose With Context.” Operational knowledge, team skills, workloads, ecosystem, and migration cost matter more than database tribalism. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 550/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 58 Tuesday, 06 October 2026 | DEPTH 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Run a second HR mock focused on weaknesses, failure, conflict, motivation, and career transitions.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Indeed Argentina ×2; Glassdoor Argentina ×1; Get on Board Argentina ×1; Torre ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | Howdy ×1; CloudDevs ×1; Proxify ×1; VanHack ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 561 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | MongoDB and GraphQL: Flexibility Needs Governance Core angle: Flexible schemas and queries need boundaries, observability, performance controls, and deliberate ownership. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “MongoDB and GraphQL: Flexibility Needs Governance” Flexible schemas and queries need boundaries, observability, performance controls, and deliberate ownership. [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “MongoDB and GraphQL: Flexibility Needs Governance.” Flexible schemas and queries need boundaries, observability, performance controls, and deliberate ownership. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 561/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 59 Wednesday, 07 October 2026 | DEPTH 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Run a second system-design mock focused on degraded dependencies, recovery, and operational ownership.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Randstad ×1; Adecco ×1; Manpower/Experis ×1; Michael Page ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | X-Team ×2; Nearsure ×1; South ×1; Strider ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 572 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | API Design Is Product Design Core angle: An API succeeds when consumers can understand, integrate, recover, and evolve without surprises. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “API Design Is Product Design” An API succeeds when consumers can understand, integrate, recover, and evolve without surprises. [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “API Design Is Product Design.” An API succeeds when consumers can understand, integrate, recover, and evolve without surprises. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 572/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 60 Thursday, 08 October 2026 | DEPTH 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Run a written exercise: transform an ambiguous business request into decisions, risks, and a delivery plan.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×2; HiringRoom employer pages ×1; Bumeran ×1; ZonaJobs ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | G2i ×1; Gun.io ×1; Lumenalta ×1; Coderio ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 583 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Debugging Is Structured Uncertainty Reduction Core angle: Form a falsifiable hypothesis, improve observability, change one variable, and preserve evidence. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “Debugging Is Structured Uncertainty Reduction” Form a falsifiable hypothesis, improve observability, change one variable, and preserve evidence. [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “Debugging Is Structured Uncertainty Reduction.” Form a falsifiable hypothesis, improve observability, change one variable, and preserve evidence. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 583/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 61 Friday, 09 October 2026 | DEPTH 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Audit the campaign tracker: orphan contacts, missing URLs, overdue follow-ups, duplicate roles, and wrong markets.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Sysarmy vacancy ×1; Nerdearla/company vacancy ×1; r/devsarg verified vacancy ×1; Get on Board Argentina ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | AgileEngine ×2; FullStack Labs ×1; Dev.Pro ×1; Encora ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 594 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | CI/CD Should Shorten the Path to Safe Feedback Core angle: Automation is valuable when it makes change smaller, evidence faster, and recovery routine. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “CI/CD Should Shorten the Path to Safe Feedback” Automation is valuable when it makes change smaller, evidence faster, and recovery routine. [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “CI/CD Should Shorten the Path to Safe Feedback.” Automation is valuable when it makes change smaller, evidence faster, and recovery routine. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 594/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 62 Saturday, 10 October 2026 | DEPTH 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Run the fourth weekly audit and compare response quality, not only response quantity.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×2; Computrabajo ×1; Indeed Argentina ×1; Torre ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | EPAM ×1; Globant ×1; Valtech ×1; Thoughtworks ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 605 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Cloud Trade-Offs Are Organizational Trade-Offs Core angle: A cloud choice changes skills, governance, cost visibility, incident ownership, and dependency risk. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Cloud Trade-Offs Are Organizational Trade-Offs” A cloud choice changes skills, governance, cost visibility, incident ownership, and dependency risk. [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Cloud Trade-Offs Are Organizational Trade-Offs.” A cloud choice changes skills, governance, cost visibility, incident ownership, and dependency risk. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 605/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 63 Sunday, 11 October 2026 | DEPTH 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Rank every active process by fit, compensation potential, compatibility, evidence required, and next action.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Experis ×1; Michael Page ×1; Glassdoor Argentina ×1; Bumeran ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Upwork long-term ×2; Workana long-term ×1; Contra long-term ×1; Malt long-term ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 616 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Platform Engineering Needs Internal Customers Core angle: A platform earns adoption by removing repeated friction for real teams, with product thinking and measurable service. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “Platform Engineering Needs Internal Customers” A platform earns adoption by removing repeated friction for real teams, with product thinking and measurable… [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “Platform Engineering Needs Internal Customers.” A platform earns adoption by removing repeated friction for real teams, with product thinking and measurable service. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 616/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 64 Monday, 12 October 2026 | PIPELINE 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Reactivate promising applications with one useful update: artifact, clarification, or availability—not a generic ping.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×2; Bumeran ×1; Computrabajo ×1; ZonaJobs ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | LinkedIn Jobs ×1; Wellfound ×1; Get on Board ×1; Remote OK ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 627 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | When to Tolerate Technical Debt Core angle: Keep debt when its interest is low and alternatives matter more; retire it when risk or drag becomes material. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “When to Tolerate Technical Debt” Keep debt when its interest is low and alternatives matter more; retire it when risk or drag becomes material. [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “When to Tolerate Technical Debt.” Keep debt when its interest is low and alternatives matter more; retire it when risk or drag becomes material. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 627/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 65 Tuesday, 13 October 2026 | PIPELINE 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Ask former colleagues for three specific references and prepare an accurate briefing packet for each.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Indeed Argentina ×1; Glassdoor Argentina ×1; Get on Board Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | YC Work at a Startup ×2; We Work Remotely ×1; Working Nomads ×1; Dynamite Jobs ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 638 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | What Old Languages Can Teach Modern Engineers Core angle: Older ecosystems expose constraints and enduring ideas about memory, data, interfaces, reliability, and change. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “What Old Languages Can Teach Modern Engineers” Older ecosystems expose constraints and enduring ideas about memory, data, interfaces, reliability, and change. [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “What Old Languages Can Teach Modern Engineers.” Older ecosystems expose constraints and enduring ideas about memory, data, interfaces, reliability, and change. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 638/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 66 Wednesday, 14 October 2026 | PIPELINE 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Create a negotiation scorecard covering cash, benefits, currency, workload, schedule, role scope, and legal compatibility.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Randstad ×2; Adecco ×1; Manpower/Experis ×1; Michael Page ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | Remotive ×1; Himalayas ×1; Jobgether ×1; Built In ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 649 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | COBOL and Mainframes: Context Before Judgment Core angle: Critical systems deserve respect for their business role, operational history, and migration risk. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “COBOL and Mainframes: Context Before Judgment” Critical systems deserve respect for their business role, operational history, and migration risk. [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “COBOL and Mainframes: Context Before Judgment.” Critical systems deserve respect for their business role, operational history, and migration risk. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 649/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 67 Thursday, 15 October 2026 | PIPELINE 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Prepare questions for CTOs: strategy, architecture, operating model, team health, delivery, and first-90-day outcomes.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; HiringRoom employer pages ×1; Bumeran ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Welcome to the Jungle ×2; JustRemote ×1; Jobspresso ×1; Remote.co ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 660 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Open Source, Ututo, and Learning in Public Core angle: Open work creates feedback, community, and durable evidence—when contribution is honest and maintainable. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Open Source, Ututo, and Learning in Public” Open work creates feedback, community, and durable evidence—when contribution is honest and maintainable. [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Open Source, Ututo, and Learning in Public.” Open work creates feedback, community, and durable evidence—when contribution is honest and maintainable. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 660/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 68 Friday, 16 October 2026 | PIPELINE 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Prepare questions for CEOs/founders: runway, product-market evidence, priorities, decision rights, and success measures.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Sysarmy vacancy ×2; Nerdearla/company vacancy ×1; r/devsarg verified vacancy ×1; Get on Board Argentina ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | NoDesk ×1; DailyRemote ×1; Remote Rocketship ×1; LATAM Jobs ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 671 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Technical Writing Is an Engineering Tool Core angle: Writing reveals ambiguity, preserves decisions, improves reviews, and makes systems easier to operate. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “Technical Writing Is an Engineering Tool” Writing reveals ambiguity, preserves decisions, improves reviews, and makes systems easier to operate. [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “Technical Writing Is an Engineering Tool.” Writing reveals ambiguity, preserves decisions, improves reviews, and makes systems easier to operate. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 671/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 69 Saturday, 17 October 2026 | PIPELINE 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Prepare questions for recruiters and HR: process, employment entity, benefits, review cadence, and contract terms.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Computrabajo ×1; Indeed Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | LatHire ×2; Puente ×1; Revelo ×1; Andela ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 682 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Teaching Makes Technical Thinking Testable Core angle: If an idea cannot be explained with examples, boundaries, and questions, it may not yet be understood. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “Teaching Makes Technical Thinking Testable” If an idea cannot be explained with examples, boundaries, and questions, it may not yet be understood. [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “Teaching Makes Technical Thinking Testable.” If an idea cannot be explained with examples, boundaries, and questions, it may not yet be understood. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 682/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 70 Sunday, 18 October 2026 | PIPELINE 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Run a referral sprint with alumni, open-source, community, client, and former-colleague networks.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Experis ×2; Michael Page ×1; Glassdoor Argentina ×1; Bumeran ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | Braintrust ×1; A.Team ×1; Arc ×1; Turing ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 693 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Mentoring Is Not Giving People Your Answers Core angle: Good mentoring improves another person’s judgment through context, questions, feedback, and progressively larger ownership. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “Mentoring Is Not Giving People Your Answers” Good mentoring improves another person’s judgment through context, questions, feedback, and progressively… [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “Mentoring Is Not Giving People Your Answers.” Good mentoring improves another person’s judgment through context, questions, feedback, and progressively larger ownership. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 693/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 71 Monday, 19 October 2026 | PIPELINE 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Revisit declined or closed roles only when there is a materially different, newly opened position.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Bumeran ×1; Computrabajo ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Toptal ×2; Lemon.io ×1; TECLA ×1; Terminal ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 704 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Translate Architecture Into Business Risk Core angle: Architecture matters when it changes continuity, speed, security, cost, adaptability, or customer experience. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “Translate Architecture Into Business Risk” Architecture matters when it changes continuity, speed, security, cost, adaptability, or customer experience. [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “Translate Architecture Into Business Risk.” Architecture matters when it changes continuity, speed, security, cost, adaptability, or customer experience. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 704/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 72 Tuesday, 20 October 2026 | PIPELINE 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Run a live pipeline review: every active application must have an owner, stage, evidence, and dated next action.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Indeed Argentina ×2; Glassdoor Argentina ×1; Get on Board Argentina ×1; Torre ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | Howdy ×1; CloudDevs ×1; Proxify ×1; VanHack ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 715 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | What Ecommerce Teaches About Reliability Core angle: Catalog, checkout, payment, inventory, and fulfillment reveal how business journeys cross many technical boundaries. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “What Ecommerce Teaches About Reliability” Catalog, checkout, payment, inventory, and fulfillment reveal how business journeys cross many technical… [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “What Ecommerce Teaches About Reliability.” Catalog, checkout, payment, inventory, and fulfillment reveal how business journeys cross many technical boundaries. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 715/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 73 Wednesday, 21 October 2026 | PIPELINE 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Simulate an offer comparison and practice asking for time, written terms, and clarification without accepting verbally.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Randstad ×1; Adecco ×1; Manpower/Experis ×1; Michael Page ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | X-Team ×2; Nearsure ×1; South ×1; Strider ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 726 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | What Banking Systems Teach About Controls Core angle: Traceability, reconciliation, authorization, resilience, and change discipline are product features in financial systems. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “What Banking Systems Teach About Controls” Traceability, reconciliation, authorization, resilience, and change discipline are product features in… [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “What Banking Systems Teach About Controls.” Traceability, reconciliation, authorization, resilience, and change discipline are product features in financial systems. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 726/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 74 Thursday, 22 October 2026 | PIPELINE 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Run the fifth weekly audit; calculate the exact remaining pace and preserve the 500/500 balance.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×2; HiringRoom employer pages ×1; Bumeran ×1; ZonaJobs ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | G2i ×1; Gun.io ×1; Lumenalta ×1; Coderio ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 737 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | What Logistics Teaches About Software Boundaries Core angle: Physical constraints, uncertain events, handoffs, and exceptions make operational truth impossible to ignore. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “What Logistics Teaches About Software Boundaries” Physical constraints, uncertain events, handoffs, and exceptions make operational truth impossible to ignore. [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “What Logistics Teaches About Software Boundaries.” Physical constraints, uncertain events, handoffs, and exceptions make operational truth impossible to ignore. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 737/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 75 Friday, 23 October 2026 | PIPELINE 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Prepare the 10/day finish phase by ranking the highest-validity sources in each market and preserving the final 500/500 balance.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Sysarmy vacancy ×1; Nerdearla/company vacancy ×1; r/devsarg verified vacancy ×1; Get on Board Argentina ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | AgileEngine ×2; FullStack Labs ×1; Dev.Pro ×1; Encora ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 748 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Billing and Batch Processing Still Matter Core angle: Correctness, idempotency, reconciliation, scheduling, and recovery remain essential even when the interface looks modern. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “Billing and Batch Processing Still Matter” Correctness, idempotency, reconciliation, scheduling, and recovery remain essential even when the interface… [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “Billing and Batch Processing Still Matter.” Correctness, idempotency, reconciliation, scheduling, and recovery remain essential even when the interface looks modern. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 748/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 76 Saturday, 24 October 2026 | PIPELINE 11 applications • 6 AR / 5 Intl |
| --- | --- |

Special focus: Refresh roles posted in the last 72 hours; speed matters only after eligibility and fit checks pass.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×2; Computrabajo ×1; Indeed Argentina ×1; Torre ×1; Direct company ATS ×1 | 6 | Specific eligible roles; approved closest-family CV |
| International | EPAM ×1; Globant ×1; Valtech ×1; Thoughtworks ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 759 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | The Consulting Mindset: Diagnose Before Prescribing Core angle: Understand goals, constraints, stakeholders, evidence, and change capacity before proposing technology. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “The Consulting Mindset: Diagnose Before Prescribing” Understand goals, constraints, stakeholders, evidence, and change capacity before proposing technology. [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “The Consulting Mindset: Diagnose Before Prescribing.” Understand goals, constraints, stakeholders, evidence, and change capacity before proposing technology. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 6/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 759/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 77 Sunday, 25 October 2026 | PIPELINE 11 applications • 5 AR / 6 Intl |
| --- | --- |

Special focus: Run an Argentina intensive across boards, recruiters, direct ATSs, and one community vacancy.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Experis ×1; Michael Page ×1; Glassdoor Argentina ×1; Bumeran ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Upwork long-term ×2; Workana long-term ×1; Contra long-term ×1; Malt long-term ×1; Direct company ATS ×1 | 6 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 22 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 770 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | What a Founder Needs From a First Engineering Leader Core angle: The first leader must balance product speed, hiring, architecture, delivery habits, and honest risk communication. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “What a Founder Needs From a First Engineering Leader” The first leader must balance product speed, hiring, architecture, delivery habits, and honest risk… [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “What a Founder Needs From a First Engineering Leader.” The first leader must balance product speed, hiring, architecture, delivery habits, and honest risk communication. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  11 valid application records; 5/6 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 770/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 78 Monday, 26 October 2026 | FINISH 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Begin the 10/day finish phase with an international intensive across remote boards, startup boards, direct ATSs, and one talent-network role.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Bumeran ×1; Computrabajo ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | LinkedIn Jobs ×1; Wellfound ×1; Get on Board ×1; Remote OK ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 780 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Interview Stories Need Decisions, Not Adjectives Core angle: A strong story shows context, responsibility, alternatives, action, result, and learning. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “Interview Stories Need Decisions, Not Adjectives” A strong story shows context, responsibility, alternatives, action, result, and learning. [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “Interview Stories Need Decisions, Not Adjectives.” A strong story shows context, responsibility, alternatives, action, result, and learning. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 780/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 79 Tuesday, 27 October 2026 | FINISH 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Refresh the LinkedIn headline, About, Featured, and Open to Work settings using evidence from current demand.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Indeed Argentina ×1; Glassdoor Argentina ×1; Get on Board Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | YC Work at a Startup ×1; We Work Remotely ×1; Working Nomads ×1; Dynamite Jobs ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 790 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Use STAR Without Sounding Scripted Core angle: STAR is a structure for clarity; natural answers still need relevance, judgment, and reflection. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “Use STAR Without Sounding Scripted” STAR is a structure for clarity; natural answers still need relevance, judgment, and reflection. [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “Use STAR Without Sounding Scripted.” STAR is a structure for clarity; natural answers still need relevance, judgment, and reflection. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 790/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 80 Wednesday, 28 October 2026 | FINISH 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Refresh every portal profile whose CV, salary, availability, or target-role fields are stale.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Randstad ×1; Adecco ×1; Manpower/Experis ×1; Michael Page ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Remotive ×1; Himalayas ×1; Jobgether ×1; Built In ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 800 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | How I Approach a System Design Interview Core angle: Clarify goals, users, scale, constraints, failure modes, data, interfaces, observability, and trade-offs before drawing boxes. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “How I Approach a System Design Interview” Clarify goals, users, scale, constraints, failure modes, data, interfaces, observability, and trade-offs… [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “How I Approach a System Design Interview.” Clarify goals, users, scale, constraints, failure modes, data, interfaces, observability, and trade-offs before drawing boxes. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 800/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 81 Thursday, 29 October 2026 | FINISH 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Run an executive-outreach quality audit and rewrite messages that could apply to any company.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; HiringRoom employer pages ×1; Bumeran ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Welcome to the Jungle ×1; JustRemote ×1; Jobspresso ×1; Remote.co ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 810 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Salary Negotiation Is Scope Negotiation Core angle: Compensation becomes easier to discuss when responsibilities, employment model, benefits, risk, and success measures are clear. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “Salary Negotiation Is Scope Negotiation” Compensation becomes easier to discuss when responsibilities, employment model, benefits, risk, and success… [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “Salary Negotiation Is Scope Negotiation.” Compensation becomes easier to discuss when responsibilities, employment model, benefits, risk, and success measures are clear. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 810/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 82 Friday, 30 October 2026 | FINISH 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Run a recruiter-outreach quality audit and make role, market, availability, and evidence immediately clear.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Sysarmy vacancy ×1; Nerdearla/company vacancy ×1; r/devsarg verified vacancy ×1; Get on Board Argentina ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | NoDesk ×1; DailyRemote ×1; Remote Rocketship ×1; LATAM Jobs ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 820 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Research a Company Before Saying Yes Core angle: Investigate product, customers, finances, leadership, engineering signals, turnover, contract terms, and role history. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Research a Company Before Saying Yes” Investigate product, customers, finances, leadership, engineering signals, turnover, contract terms, and role… [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Research a Company Before Saying Yes.” Investigate product, customers, finances, leadership, engineering signals, turnover, contract terms, and role history. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 820/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 83 Saturday, 31 October 2026 | FINISH 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Review content analytics for recruiter visits, profile views, meaningful comments, and inbound conversations.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Computrabajo ×1; Indeed Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | LatHire ×1; Puente ×1; Revelo ×1; Andela ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 830 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Questions That Reveal the Real Job Core angle: Ask about first outcomes, decision authority, constraints, team health, on-call, delivery pressure, and why the role is open. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “Questions That Reveal the Real Job” Ask about first outcomes, decision authority, constraints, team health, on-call, delivery pressure, and why… [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “Questions That Reveal the Real Job.” Ask about first outcomes, decision authority, constraints, team health, on-call, delivery pressure, and why the role is open. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 830/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 84 Sunday, 01 November 2026 | FINISH 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Turn the best-performing article into a portfolio landing page and link it from LinkedIn Featured.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Experis ×1; Michael Page ×1; Glassdoor Argentina ×1; Bumeran ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Braintrust ×1; A.Team ×1; Arc ×1; Turing ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 840 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Choose References Before You Need Them Core angle: Select people who can verify relevant work, brief them honestly, and make the request easy to decline. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “Choose References Before You Need Them” Select people who can verify relevant work, brief them honestly, and make the request easy to decline. [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “Choose References Before You Need Them.” Select people who can verify relevant work, brief them honestly, and make the request easy to decline. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 840/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 85 Monday, 02 November 2026 | FINISH 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Complete an interview-day readiness check: environment, connection, camera, audio, notes, examples, and questions.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Bumeran ×1; Computrabajo ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Toptal ×1; Lemon.io ×1; TECLA ×1; Terminal ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 850 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Predictable Teams Are Not Slow Teams Core angle: Clear priorities, small changes, fast feedback, quality controls, and visible risk make speed repeatable. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “Predictable Teams Are Not Slow Teams” Clear priorities, small changes, fast feedback, quality controls, and visible risk make speed repeatable. [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “Predictable Teams Are Not Slow Teams.” Clear priorities, small changes, fast feedback, quality controls, and visible risk make speed repeatable. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 850/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 86 Tuesday, 03 November 2026 | FINISH 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Run a third system-design mock using a domain from the target company’s real product.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Indeed Argentina ×1; Glassdoor Argentina ×1; Get on Board Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Howdy ×1; CloudDevs ×1; Proxify ×1; VanHack ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 860 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Application Support Is Product Intelligence Core angle: Support sees recurring failure, user friction, operational gaps, and hidden dependencies that should inform roadmaps. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “Application Support Is Product Intelligence” Support sees recurring failure, user friction, operational gaps, and hidden dependencies that should inform… [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “Application Support Is Product Intelligence.” Support sees recurring failure, user friction, operational gaps, and hidden dependencies that should inform roadmaps. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 860/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 87 Wednesday, 04 November 2026 | FINISH 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Run a third leadership mock focused on organizational scale, delegation, and difficult trade-offs.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Randstad ×1; Adecco ×1; Manpower/Experis ×1; Michael Page ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | X-Team ×1; Nearsure ×1; South ×1; Strider ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 870 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Solutions Engineering Lives Between Truths Core angle: The role connects customer reality, product capability, technical feasibility, and implementation risk. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Solutions Engineering Lives Between Truths” The role connects customer reality, product capability, technical feasibility, and implementation risk. [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Solutions Engineering Lives Between Truths.” The role connects customer reality, product capability, technical feasibility, and implementation risk. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 870/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 88 Thursday, 05 November 2026 | FINISH 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Audit compensation assumptions against live conversations; update targets only with real market evidence.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; HiringRoom employer pages ×1; Bumeran ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | G2i ×1; Gun.io ×1; Lumenalta ×1; Coderio ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 880 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Technical Account Management Is Proactive Engineering Core angle: Great TAM work uses context, telemetry, relationships, and escalation discipline to protect customer outcomes. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “Technical Account Management Is Proactive Engineering” Great TAM work uses context, telemetry, relationships, and escalation discipline to protect customer outcomes. [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “Technical Account Management Is Proactive Engineering.” Great TAM work uses context, telemetry, relationships, and escalation discipline to protect customer outcomes. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 880/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 89 Friday, 06 November 2026 | FINISH 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Run the sixth weekly audit and identify the shortest credible path from each live process to a decision.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Sysarmy vacancy ×1; Nerdearla/company vacancy ×1; r/devsarg verified vacancy ×1; Get on Board Argentina ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | AgileEngine ×1; FullStack Labs ×1; Dev.Pro ×1; Encora ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 890 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | The Modern IT Manager as a Risk Integrator Core angle: IT leadership connects identity, endpoints, networks, vendors, support, continuity, security, and business priorities. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “The Modern IT Manager as a Risk Integrator” IT leadership connects identity, endpoints, networks, vendors, support, continuity, security, and business… [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “The Modern IT Manager as a Risk Integrator.” IT leadership connects identity, endpoints, networks, vendors, support, continuity, security, and business priorities. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 890/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 90 Saturday, 07 November 2026 | FINISH 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Review contract clauses for every serious process and create a written list of unresolved questions.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Computrabajo ×1; Indeed Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | EPAM ×1; Globant ×1; Valtech ×1; Thoughtworks ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 900 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | What an Observability Engineer Should Optimize Core angle: Optimize for faster understanding and safer action, not the number of dashboards, agents, or retained events. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “What an Observability Engineer Should Optimize” Optimize for faster understanding and safer action, not the number of dashboards, agents, or retained events. [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “What an Observability Engineer Should Optimize.” Optimize for faster understanding and safer action, not the number of dashboards, agents, or retained events. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 900/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 91 Sunday, 08 November 2026 | FINISH 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Protect delivery quality in the current role while scheduling interviews and search work responsibly.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Experis ×1; Michael Page ×1; Glassdoor Argentina ×1; Bumeran ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Upwork long-term ×1; Workana long-term ×1; Contra long-term ×1; Malt long-term ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 910 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Contract Clauses Engineers Should Read Core angle: Exclusivity, IP, outside work, confidentiality, non-compete, schedule, termination, and governing law can change the real offer. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “Contract Clauses Engineers Should Read” Exclusivity, IP, outside work, confidentiality, non-compete, schedule, termination, and governing law can… [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “Contract Clauses Engineers Should Read.” Exclusivity, IP, outside work, confidentiality, non-compete, schedule, termination, and governing law can change the real offer. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 910/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 92 Monday, 09 November 2026 | CLOSE 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Run a final referral round for named openings; do not send vague requests to entire networks.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Bumeran ×1; Computrabajo ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | LinkedIn Jobs ×1; Wellfound ×1; Get on Board ×1; Remote OK ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 920 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Can Two Full-Time Roles Be Compatible? Core angle: Compatibility requires lawful contracts, truthful disclosure where required, non-overlapping commitments, and dependable performance. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Can Two Full-Time Roles Be Compatible?” Compatibility requires lawful contracts, truthful disclosure where required, non-overlapping commitments, and… [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Can Two Full-Time Roles Be Compatible?.” Compatibility requires lawful contracts, truthful disclosure where required, non-overlapping commitments, and dependable performance. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 920/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 93 Tuesday, 10 November 2026 | CLOSE 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Close dead tracker records with a reason and reactivate only those with a specific new trigger.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Indeed Argentina ×1; Glassdoor Argentina ×1; Get on Board Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | YC Work at a Startup ×1; We Work Remotely ×1; Working Nomads ×1; Dynamite Jobs ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 930 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Treat Rejection as Data Without Losing Perspective Core angle: Classify rejection stages and hypotheses, but avoid inventing certainty from a single outcome. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “Treat Rejection as Data Without Losing Perspective” Classify rejection stages and hypotheses, but avoid inventing certainty from a single outcome. [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “Treat Rejection as Data Without Losing Perspective.” Classify rejection stages and hypotheses, but avoid inventing certainty from a single outcome. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 930/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 94 Wednesday, 11 November 2026 | CLOSE 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Prepare a first-30/60/90-day hypothesis for the strongest active opportunity without overpromising.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Randstad ×1; Adecco ×1; Manpower/Experis ×1; Michael Page ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Remotive ×1; Himalayas ×1; Jobgether ×1; Built In ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 940 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | A Follow-Up Should Add Signal Core angle: A useful follow-up is brief, timely, specific, and may add a relevant artifact or clarification. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “A Follow-Up Should Add Signal” A useful follow-up is brief, timely, specific, and may add a relevant artifact or clarification. [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “A Follow-Up Should Add Signal.” A useful follow-up is brief, timely, specific, and may add a relevant artifact or clarification. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 940/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 95 Thursday, 12 November 2026 | CLOSE 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Run a final HR mock with randomized questions from the low-confidence queue.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; HiringRoom employer pages ×1; Bumeran ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Welcome to the Jungle ×1; JustRemote ×1; Jobspresso ×1; Remote.co ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 950 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Executive Outreach: Earn the Right to Be Read Core angle: Demonstrate that you understand the company, connect one credible capability to one problem, and ask for a small next step. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “Executive Outreach: Earn the Right to Be Read” Demonstrate that you understand the company, connect one credible capability to one problem, and ask for a… [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “Executive Outreach: Earn the Right to Be Read.” Demonstrate that you understand the company, connect one credible capability to one problem, and ask for a small next step. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 950/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 96 Friday, 13 November 2026 | CLOSE 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Run a final technical mock across architecture, debugging, data, Linux, and operational trade-offs.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Sysarmy vacancy ×1; Nerdearla/company vacancy ×1; r/devsarg verified vacancy ×1; Get on Board Argentina ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | NoDesk ×1; DailyRemote ×1; Remote Rocketship ×1; LATAM Jobs ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 960 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | How to Ask for a Referral Respectfully Core angle: Name the role, explain fit in two lines, provide materials, and make declining completely comfortable. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | New article: “How to Ask for a Referral Respectfully” Name the role, explain fit in two lines, provide materials, and make declining completely comfortable. [ARTICLE LINK] #SoftwareEngineering |
| LinkedIn | A strong technical career is built from decisions that can be explained—not a list of tools. New article: “How to Ask for a Referral Respectfully.” Name the role, explain fit in two lines, provide materials, and make declining completely comfortable. How does your team approach it? Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 960/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 97 Saturday, 14 November 2026 | CLOSE 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Run a final negotiation rehearsal covering base, upside, benefits, currency, review, start date, and compatibility.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Computrabajo ×1; Indeed Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | LatHire ×1; Puente ×1; Revelo ×1; Andela ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 970 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | Publishing During a Job Search Core angle: Consistent content can demonstrate judgment and communication when it is useful, truthful, and connected to target work. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s field note: “Publishing During a Job Search” Consistent content can demonstrate judgment and communication when it is useful, truthful, and connected to… [ARTICLE LINK] #EngineeringLeadership |
| LinkedIn | The interesting part of engineering is rarely the slogan; it is the trade-off underneath it. New article: “Publishing During a Job Search.” Consistent content can demonstrate judgment and communication when it is useful, truthful, and connected to target work. I’d be interested in what experience has taught you. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 970/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 98 Sunday, 15 November 2026 | CLOSE 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Run the penultimate quality audit for duplicates, invalid locations, missing evidence, and overdue follow-ups; repair the records before the final two days.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Experis ×1; Michael Page ×1; Glassdoor Argentina ×1; Bumeran ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Braintrust ×1; A.Team ×1; Arc ×1; Turing ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 980 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | 1,000 Applications: Quality Versus Volume Is the Wrong Debate Core angle: The useful system uses volume for reach and controls for eligibility, fit, truth, tailoring, and learning. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | I wrote about a practical engineering lesson: “1,000 Applications: Quality Versus Volume Is the Wrong Debate” The useful system uses volume for reach and controls for eligibility, fit, truth, tailoring, and learning. [ARTICLE LINK] #TechCareers |
| LinkedIn | One lesson keeps returning across software, infrastructure, and leadership work: New article: “1,000 Applications: Quality Versus Volume Is the Wrong Debate.” The useful system uses volume for reach and controls for eligibility, fit, truth, tailoring, and learning. The post turns the idea into a practical checklist. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 980/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 99 Monday, 16 November 2026 | CLOSE 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Submit ten valid applications, verify 990 cumulative records and the 495/495 balance, and prepare the final-day shortlist.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | LinkedIn Jobs ×1; Bumeran ×1; Computrabajo ×1; ZonaJobs ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Toptal ×1; Lemon.io ×1; TECLA ×1; Terminal ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. No new referral quota today; reply to any referral conversation already open.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 990 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | What a 100-Day Job Campaign Reveals Core angle: A long campaign makes positioning, channel quality, discipline, energy, and conversion visible enough to improve. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | A new note from the 100-day series: “What a 100-Day Job Campaign Reveals” A long campaign makes positioning, channel quality, discipline, energy, and conversion visible enough to… [ARTICLE LINK] #DevOps |
| LinkedIn | I’m documenting practical lessons from engineering and leadership during this 100-day campaign. New article: “What a 100-Day Job Campaign Reveals.” A long campaign makes positioning, channel quality, discipline, energy, and conversion visible enough to improve. I hope it helps people building dependable systems and teams. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 990/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

| Day 100 Tuesday, 17 November 2026 | CLOSE 10 applications • 5 AR / 5 Intl |
| --- | --- |

Special focus: Submit the final ten valid applications, close the 500/500 totals, and produce the campaign retrospective.

| Market | Exact source allocation | Apps | Validation |
| --- | --- | --- | --- |
| Argentina | Indeed Argentina ×1; Glassdoor Argentina ×1; Get on Board Argentina ×1; Torre ×1; Direct company ATS ×1 | 5 | Specific eligible roles; approved closest-family CV |
| International | Howdy ×1; CloudDevs ×1; Proxify ×1; VanHack ×1; Direct company ATS ×1 | 5 | Argentina accepted; approved closest-family CV |

EXECUTE TODAY — IN ORDER

☐ Source and pre-screen at least 20 roles from the channels above; reject duplicates, closed roles, location exclusions, and <60% fits.

☐ AI copilot ranks the shortlist, selects the CV family, and flags evidence-only keyword gaps; candidate approves roles and all factual edits.

☐ Tailor one priority AR and one priority international CV. Use a cover letter only when required or useful; submit the remaining roles with the closest approved CV.

☐ Log each submission immediately: company, role, canonical URL, source, market, CV, salary/rate, contact, date, and follow-up.

☐ Send 4 new messages: one recruiter and one CTO/CEO/hiring manager in each market. Each must reference a real role or company need.

☐ Send 4 due follow-ups. Send one warm referral request for a named opening.

☐ Complete the special focus; publish the article, LinkedIn, X, and Instagram Story; process replies; close at 1000 cumulative applications.

DAILY BLOG + DISTRIBUTION

| Blog | The Next Chapter Starts With Evidence Core angle: A job search ends well when the decision reflects verified role reality, fair terms, sustainable commitments, and mutual value. Draft: problem/context → 3 practical lessons → example or checklist → honest CTA. Target 600–900 words; fact-check and anonymize. |
| --- | --- |
| X | Today’s post: “The Next Chapter Starts With Evidence” A job search ends well when the decision reflects verified role reality, fair terms, sustainable commitments,… [ARTICLE LINK] #Leadership |
| LinkedIn | Today I’m sharing a concise framework I would use with a team, a candidate, or a client. New article: “The Next Chapter Starts With Evidence.” A job search ends well when the decision reflects verified role reality, fair terms, sustainable commitments, and mutual value. I’m glad to compare notes with engineers and technical leaders. Read: [ARTICLE LINK] #SoftwareEngineering #EngineeringLeadership #TechCareers |
| Instagram | ☐ Create and publish one Story manually using the article title, one useful takeaway, and [ARTICLE LINK]. Save the live Story/link evidence in the Plan tab. |

CLOSE-DAY PROOF  10 valid application records; 5/5 market split; 4 new outreach messages; 4 follow-ups; content links; replies processed; cumulative 1000/1,000. If any portal slot failed, the same-market direct-ATS replacement and reason are logged.

REUSABLE ASSETS

# Application, outreach, and negotiation templates

Copy only after replacing every bracketed field with truthful, role-specific information.

PERSONALIZATION STANDARD A message is ready only when it names the company or role, connects one relevant fact to one plausible need, includes one evidence link when useful, and asks for a small next step. Delete unused placeholders.

### International recruiter — English

Hi [NAME] — I’m a [TARGET ROLE] based in Argentina with experience in [RELEVANT SCOPE/STACK] and [VERIFIABLE OUTCOME]. I’m interested in [ROLE] because [SPECIFIC FIT]. Does the team hire from Argentina, and would a short conversation be useful? CV: [LINK].

### Argentina recruiter — Spanish

Hola [NOMBRE]. Soy [ROL OBJETIVO] con experiencia en [ALCANCE/STACK RELEVANTE] y [RESULTADO VERIFICABLE]. Me interesa [PUESTO] por [ENCAJE ESPECÍFICO]. ¿Te parece útil una conversación breve? CV: [ENLACE].

### CTO/CEO — English

Hi [NAME] — I noticed [COMPANY] is [SPECIFIC SIGNAL]. I’ve handled [RELEVANT PROBLEM] in [CONTEXT], including [EVIDENCE/OUTCOME]. If [PLAUSIBLE NEED] is a current priority, I’d be glad to compare notes in a 15-minute call. [LINK].

### CTO/CEO — Spanish

Hola [NOMBRE]. Vi que [EMPRESA] está [SEÑAL ESPECÍFICA]. Trabajé sobre [PROBLEMA RELEVANTE] en [CONTEXTO], con [EVIDENCIA/RESULTADO]. Si [NECESIDAD POSIBLE] es prioridad, con gusto comparo ideas en una charla de 15 minutos. [ENLACE].

### Hiring manager

Hi [NAME] — I applied for [ROLE] today. The closest connection is [REQUIREMENT] ↔ [YOUR EVIDENCE]. I also wrote/built [ARTIFACT] showing how I approach [PROBLEM]: [LINK]. No action needed if the process is already covered; I wanted to add useful context.

### Referral request

Hi [NAME] — I’m considering [ROLE] at [COMPANY]: [LINK]. My strongest fit is [TWO-LINE EVIDENCE]. If you know the team and feel comfortable, would you introduce me or share how the role really works? Absolutely no problem if not. I can send a short CV and note.

### First follow-up

Hi [NAME] — following up on [ROLE/CONVERSATION] from [DATE]. One relevant addition: [NEW ARTIFACT, RESULT, OR CLARIFICATION]. I remain interested because [SPECIFIC REASON]. Is there any information that would help the team decide on next steps?

### Post-interview thank-you

Thank you for today’s conversation about [ROLE]. The discussion about [SPECIFIC TOPIC] reinforced my interest. My experience with [EVIDENCE] seems especially relevant to [NEED]. I’ve included [PROMISED ITEM]. Please let me know if another example would be useful.

### Short cover letter — English

Dear [TEAM], I’m applying for [ROLE] because [SPECIFIC COMPANY/ROLE REASON]. In [CONTEXT], I [ACTION] and achieved [VERIFIABLE RESULT], which maps directly to [REQUIREMENT]. I can also contribute [SECOND RELEVANT CAPABILITY]. I am based in Argentina and [TRUTHFUL EMPLOYMENT/TIMEZONE NOTE]. I would welcome a conversation about [FIRST OUTCOME].

### Carta breve — español

Hola [EQUIPO]. Me postulo a [PUESTO] porque [MOTIVO ESPECÍFICO]. En [CONTEXTO], [ACCIÓN] y logré [RESULTADO VERIFICABLE], experiencia directamente relacionada con [REQUISITO]. También puedo aportar [SEGUNDA CAPACIDAD]. Estoy en Argentina y [NOTA REAL SOBRE MODALIDAD/DISPONIBILIDAD]. Me gustaría conversar sobre [PRIMER RESULTADO].

### Salary — English

Before I anchor the discussion, what range has been approved for the role? Based on the scope we’ve discussed, the employment model, and total package, I’m targeting [RANGE] [CURRENCY] per month, with flexibility for the right responsibilities and terms.

### Salary — Spanish

Antes de fijar una expectativa, ¿qué rango tiene aprobado la empresa para el puesto? Por el alcance conversado, la modalidad de contratación y la compensación total, apunto a [RANGO] [MONEDA] mensuales, con flexibilidad según responsabilidades y condiciones.

### Outside-employment / contract question

Before accepting, I want to confirm the written policy on outside employment, exclusivity, IP assignment, non-compete obligations, working hours, on-call coverage, confidentiality, and equipment. I will comply with required disclosure or approval and avoid any conflict or overlap.

DAY 5 DELIVERABLE

# Classic HR FAQ database blueprint

The database supplies generic bilingual answers that become personal only after verified placeholders are completed.

| Category | Examples | Rows |
| --- | --- | --- |
| Introduction & background | Tell me about yourself; walk me through your résumé; career story | 15 |
| Motivation & fit | Why this role/company; why leave; what motivates you | 15 |
| Strengths & weaknesses | Best strength; development area; feedback; self-awareness | 12 |
| Teamwork & conflict | Disagreement; difficult colleague; collaboration; trust | 15 |
| Leadership & management | Delegation; performance; hiring; influence; change | 18 |
| Failure & resilience | Mistake; missed goal; rejection; pressure; recovery | 12 |
| Remote work & time | Communication; focus; priorities; timezone; autonomy | 12 |
| Career changes & gaps | Transitions; short tenure; overqualification; gaps | 10 |
| Salary & logistics | Expectations; availability; location; travel; start date | 15 |
| Ethics & work compatibility | Conflicts; confidentiality; outside work; integrity | 10 |
| Company culture & closing | Manager style; environment; questions; next steps | 16 |
| Total | Bilingual generic answer rows | 150 |

## Answer architecture

Direct answer in the first sentence. Avoid autobiography before answering the actual question.

One compact principle or rationale that works across candidates.

A clearly marked placeholder for one verified personal example, metric, context, or preference.

A positive connection to the role when relevant; never force a company compliment.

A natural stopping point at 45–90 seconds, plus likely follow-up prompts for deeper discussion.

## Twelve starter patterns

| Question | Generic answer pattern | Evaluates | Avoid |
| --- | --- | --- | --- |
| Tell me about yourself | I’m a [ROLE] with experience in [2–3 RELEVANT AREAS]. Recently, I [VERIFIED SCOPE/OUTCOME]. I’m now looking for [TARGET] where I can contribute [VALUE]. | Relevance and narrative | Full life history |
| Why do you want this role? | The role combines [RESPONSIBILITY] and [PROBLEM], which match my experience in [EVIDENCE]. I’m also interested in [SPECIFIC COMPANY FACT]. | Motivation and research | Generic praise |
| What is your greatest strength? | A consistent strength is [STRENGTH]. In [CONTEXT], it helped me [ACTION/RESULT]. I apply it by [BEHAVIOR]. | Self-awareness and proof | Unsupported adjective |
| What is a weakness? | I’m improving [REAL, NON-FATAL AREA]. I noticed it through [SIGNAL], changed [BEHAVIOR], and now measure progress through [CHECK]. | Honesty and learning | A disguised strength |
| Why are you leaving? | I’m looking for [FORWARD-LOOKING NEED] that is limited in my current context. I value what I learned there and want to apply it to [TARGET]. | Judgment and professionalism | Attacking employer |
| Describe a conflict | I first clarified the shared goal and each constraint. We agreed on [DECISION METHOD], tested [OPTION], and reached [RESULT/LEARNING]. | Collaboration under tension | Blame or avoidance |
| Tell me about a failure | In [SITUATION], I was responsible for [DECISION]. The result was [IMPACT]. I corrected [ACTION] and changed [SYSTEM/BEHAVIOR] to prevent recurrence. | Accountability and growth | Minimizing impact |
| How do you prioritize? | I compare impact, urgency, risk, dependencies, effort, and reversibility, then make the trade-off visible to stakeholders and revisit it with new evidence. | Decision discipline | “Everything is urgent” |
| Salary expectations? | What range is approved? Based on scope and total package, I’m targeting [RANGE], with flexibility for responsibilities and terms. | Market awareness | Leading with minimum |
| When can you start? | I can start after [TRUTHFUL NOTICE/COMMITMENTS]. Before confirming, I would align on working hours, onboarding, and any required outside-employment approval. | Reliability and logistics | Impossible promise |
| Why should we hire you? | The strongest match is [NEED] and my evidence in [OUTCOME]. I also bring [SECOND VALUE]. I would validate this through [FIRST-90-DAY APPROACH]. | Value and confidence | Comparing against unknown candidates |
| Do you have questions? | Yes: what outcomes define success in 90 days, what makes the role hard today, who owns key decisions, and why is the role open? | Curiosity and judgment | Only asking benefits |

DAY 5 QUALITY GATE Every answer must be generic, defensible, bilingual, concise, and clearly marked where personal facts are required. The platform must never present placeholders as finished answers.

CAMPAIGN CONTROL

# Tracker field reference and weekly review

The counter is a consequence of valid records—not a manually edited number.

| Group | Required fields |
| --- | --- |
| Identity | Application ID; company; role; canonical URL; market; location eligibility |
| Source | Discovery platform; submission ATS; recruiter/contact; referral; campaign day |
| Fit | Role family; fit score; must-haves met/missing; truthful keyword notes |
| Assets | CV family/language/version; cover letter; application note; evidence link |
| Commercial | Displayed range; stated expectation; currency; employment model; benefits notes |
| Process | Applied timestamp; stage; next action; follow-up due/sent; response; interviews |
| Outcome | Offer/rejection/closed; known reason; hypothesis; lessons; reapply date if legitimate |
| Audit | Created/updated timestamps; duplicate warning; validation flags; notes |

## Weekly review — every seventh application day

Reconcile submitted applications against confirmation emails and ATS records; remove any invalid counts.

Check cumulative total and 500/500 split; compute the required daily pace for remaining application days.

Compare response and interview conversion by source, market, role family, CV, and week. Use minimum sample sizes before declaring winners.

Read every reply and rejection category; separate known reasons from hypotheses.

Audit content streak, profile views, recruiter visits, meaningful comments, inbound messages, and best-performing topics.

Choose one controlled experiment for the next week. Change one major variable at a time.

Review workload and current-job performance. Reschedule search work before it creates an ethical, health, or delivery problem.

## Recovery rule

IF THE CAMPAIGN FALLS BEHIND Required pace = ceiling((1,000 − valid submitted) ÷ remaining application days). Preserve market balance separately. Add no more than two applications above the planned day without first checking quality and workload; spread larger deficits across the remaining schedule.

## Final decision gate

| Dimension | Questions before accepting |
| --- | --- |
| Role reality | What will I own? What are the first 90-day outcomes? Why is the role open? |
| Compensation | Base, currency, gross/net, fees, benefits, bonus, review cadence, inflation/FX exposure? |
| Time | Working hours, timezone, meetings, on-call, travel, start date, schedule overlap? |
| Compatibility | Outside-work approval, exclusivity, conflict, IP, non-compete, confidentiality, equipment? |
| Company | Runway/financial health, leadership, product, customers, turnover, engineering practices? |
| Risk | Termination, notice, probation, governing law, contractor classification, payment reliability? |
| Evidence | Are all material promises written in the offer or contract? What remains ambiguous? |

DAY 100 IS NOT THE GOAL

A compatible, well-paid,
truthful next role is the goal.

The plan creates reach. The tracker creates evidence. The content creates public proof. The interviews create mutual understanding. The contract decides whether the opportunity is genuinely right.

| 1,000 APPLICATIONS | 500 / 500 MARKET SPLIT | 100 PUBLISHED POSTS |
| --- | --- | --- |